| NGMP 2019-2022 Proposal Request Summary |  |  |
| --- | --- | --- |
| - Proposal Title | Sea-ice monitoring to support resilient transportation infrastructure, community economic development and youth training in Gjoa Haven and Taloyoak, Nunavut |  |
| - Proposal Date | February 28, 2019 |  |
| - Valued Component (VC) and associated indicator(s) | Primary Theme: Transportation Infrastructure & Activity Indicator(s): - Reduction in SAR incidents | Secondary Theme: Economy Valued Component: Economic Activity |
| - Location | Region: Kitikmeot Communities: Gjoa Haven (68°N, 95°W) Taloyoak (69°N, 93°W) |  |
| - Project Lead, Affiliation and Contact Information | Connie Baines, Community Development Coordinator, Hamlet of Gjoa Haven, P.O. Box 200, Gjoa Haven, NU, X0B 1J0; 613-207-1986; edogjoa@qiniq.com |  |
| - Key Project Team Members and their Affiliations | Project Co-leads Peter Aqqaq, Community Economic Development Officer, Hamlet of Taloyoak Dr. Trevor Bell, Founder/Director of SmartICE Project Team Members Dr. Alain Leclair, Director of Science and Technology, Polar Knowledge Canada. Andrew Arreak, Nunavut Operations Lead (Qikiqtaaluk North), Robert Karetak, Nunavut Operations Lead (Kivalliq), SmartICE Shelly Elverum, Community Capacity and Support, SmartICE Tyler Spurrell, Technical Operations Lead, SmartICE |  |
| - Brief Plain Language Summary | This project will involve the expansion of SmartICE sea-ice monitoring services to the communities of Gjoa Haven and Taloyoak in the Kitikmeot region, over a period of three years from 2019/20 to 2021/22. Through the use of stationary and mobile ice-thickness sensing equipment, monitoring services can help to mitigate the ongoing impacts of climate change. These impacts, particularly on the formation and break-up of landfast sea-ice, are clearly being felt in northern communities. Travel safety, access to country foods, and the ability to participate in economic, cultural and family activities are particularly affected, with significant repercussions for physical and mental well-being. Sea-ice monitoring services can be introduced through a process consisting of several steps, including respectful engagement of the community, creation of a sea-ice user group (Sikumiut), procurement and deployment of stationary and mobile sensing equipment, hiring and training of operators, establishment of a community data portal, training of youth in IQ/traditional knowledge, and co-development of a sustainability plan. The resulting monitoring, documentation and communication of sea-ice conditions will provide an improved understanding of how community ice travel routes in Gjoa Haven and Taloyoak are impacted by climate change effects. More effective documentation can help to determine and inform actions for adapting to these changes, ultimately providing for safer travel in areas around the communities and greater opportunities to pursue economic and cultural activities. |  |
| - Project description - Purpose and Objectives | Sea ice is a critical infrastructure in Inuit communities for most of the year but is becoming less predictable as climate changes (Bell and Brown 2018). Such unpredictability represents a significant risk for personal travel safety and community wellbeing. Sea-ice monitoring services and information, co-developed through a partnership between the communities of Gjoa Haven and Taloyoak and SmartICE, can help mitigate the effects of increasingly unpredictable ice conditions creating benefits for a cross-section of stakeholders. First, the effective and efficient distribution of more comprehensive sea-ice information (including thickness data and locally-identified conditions) will improve confidence in sea-ice travel routes and reduce travel risks. As the ability to travel safely over sea-ice is a necessity in northern communities, particularly between Gjoa Haven and Taloyoak as the communities are inter-connected in many ways, enhanced monitoring of traditional routes should have significant outcomes once implemented, primarily in the number of Search and Rescue (SAR) incidents and confidence in travel routes. Sea-ice monitoring will also provide employment and skill development opportunities to community members. In each community, 2 operators will be identified by the Sikumiut groups, and then hired to conduct ongoing sea-ice monitoring activities. The development of transferrable skill sets will also be fostered in local operators through training in safe operation of SmartICE equipment, which includes software and hardware technology use, data acquisition and reporting protocols, computer-supported mapping and service delivery standards. Finally, sea-ice monitoring activities will enhance access to both economic and recreational/cultural activities for community residents. In terms of economic activities, commercial fishing operations and carving stone transportation are both highly relevant to the two communities and highly dependent on travel over sea-ice trails. Greater confidence in travel routes will provide more consistent access to these resources and therefore result in economic benefits for community businesses. Additionally, community members also use sea-ice trails to access country foods and to maintain cultural and family practices. As a result, unpredictable ice conditions can have severe repercussions for food security, the ability to maintain sustainable livelihoods and physical and mental health. |  |
| - Brief Rationale | Introduction of SmartICE services will result in enhanced monitoring of the changing sea-ice conditions resulting from climate change and will help to address the impacts that these changes have on the safety of sea-ice travel routes. SmartICE, a work-integrated social enterprise operating on a business model consistent with Inuit societal values, is the proprietor of the world’s first climate change adaptation tool to integrate traditional knowledge of sea ice with advanced data acquisition and remote monitoring technology. The system combines these approaches to provide invaluable, data-driven insights into sea-ice thickness and local ice conditions, in near real-time. The primary components of the SmartICE system are: - A network of in-situ sensors (SmartBUOYs) - Mobile sensors (SmartQAMUTIKs), and - Information technology integrates in situ and remotely sensed sea ice data to generate raw and processed digital products that match the needs of user groups. Central to success is the SmartICE community operator who works closely with a community sea-ice user group (Sikumiut) to understand where and when sea ice is most hazardous, how SmartICE can operate to address local information needs, and in which ways Inuit knowledge can be incorporated with SmartICE technology. This system of monitoring technology combined with local operators and user groups works to fill a gap that currently exists in ice monitoring services. For Inuit living in remote coastal communities and travelling on unsafe ice, the key barriers to climate change adaptation are availability of suitable sea-ice information at appropriate spatial scales and in a format that is both comprehensible and accessible in a timely manner. The SmartICE information system directly supports better decision-making across sectors. It benefits public safety, food security, and health and wellbeing. In Gjoa Haven and Taloyoak in particular, commercial fishing operations and carving stone transportation have been identified as key areas where SmartICE can play a supporting role, in addition to ensuring access to country foods, recreational activities and travel routes between the two communities. |  |
| - Project Duration | Duration: 3 years Start Date: April 1st, 2019 End Date: March 31st, 2022 |  |
| - Inuit Qaujimajatuqangit (IQ) and Traditional Knowledge | IQ and Traditional Knowledge will primarily be integrated into the project through consultation with elders and community organizations in the co-development of sea-ice monitoring services and associated training activities. Elders and Sikumiut members will be the source of knowledge in documenting terminology and local ice conditions and also in determining the and traditional travel routes to be monitored using the mobile sensing technology. Elders and Sikumiut members will also play an active role in training activities by providing on-ice instruction to youth. Finally, these groups can be involved in sustainability planning processes, ultimately ensuring future developments are aligned with Inuit traditional values and serve the best interests of the communities. |  |
| - Communications and Reporting | This is a community driven project with support letters from both the Hamlet of Gjoa Haven and Taloyoak and the Hunters and Trappers Organizations from both communities. Once sea-ice monitoring services are implemented, this relevant information can be communicated and distributed through various formats. These can include viewing the data through the SIKU online portal, on TV displays installed in public areas of community buildings and on printouts that can be distributed to sea-ice users. These various formats help to ensure that important information is available wherever needed, regardless of technological capabilities or access to internet connections. SmartICE has committed to work with project partners to contribute to any communication activities that are planned over the life the project and document work in the classroom and on ice. We will commit to being proactive and work with all partners involved to jointly release news stories of progress and milestones. We anticipate reporting yearly and at defined timelines and benchmarks of the project. Sensor generated data is safely stored and will be reported back through the SIKU platform. SmartICE partners with SIKU to make data available in communities where SmartICE equipment exists. The Inuit Knowledge Wiki & Social Mapping Platform, SIKU, the Inuktitut word for sea ice, is a social media mapping platform and mobile app designed with and for Inuit combining traditional knowledge and tools with cutting edge technology. It improves novel ways to document and mobilize youth, community health, education and environmental stewardship. |  |
| - Deliverables | - Distribution through various methods of sea-ice monitoring information, built upon IQ, satellite imagery, and mobile and stationary sea-ice thickness monitoring technology - Training plan to train youth in operation of SmartICE monitoring equipment and documentation of IQ terminology - Sustainability plan, co-developed with EDO’s, that involves regional support and commercial clients for community-operated SmartICE services |  |
| - Budget Summary | The total requested funding for this project is $300,000 Yearly Breakdown: Year 1: $174,666 Year 2: $113,667 Year 3: $11,667 *See Appendix B for the detailed project budget |  |