NIRB File No.: 19TN032

NPC File No.: 149064

July 19, 2019

| To: The Honourable Catherine McKenna, P.C. Minister of Environment and Climate Change Government of Canada House of Commons Ottawa, ON K1A 0A6 | The Honourable Marc Garneau, P.C. Minister of Transport Government of Canada House of Commons Ottawa, ON K1A 0A6 |
| --- | --- |

Sent via email: ec.ministre-minister.ec@canada.ca, catherine.mckenna@parl.gc.ca and questions@tc.gc.ca

Re:	Extension Request for NIRB Screening of “MS ROALD AMUNDSEN: Northwest Passage – In the Footsteps of Roald Amundsen” Project Proposal

Dear Honourable Ministers:

On May 23, 2019 the Nunavut Impact Review Board (NIRB or Board) received a referral to screen Hurtigruten AS’s (Hurtigruten) “MS ROALD AMUNDSEN: Northwest Passage – In the Footsteps of Roald Amundsen” project proposal from the Nunavut Planning Commission for screening, pursuant to Part 3 of the Nunavut Planning and Project Assessment Act, S.C. 2013, c. 14, s. 2 (NuPPAA).  Pursuant to s. 92(4) of the NuPPAA, the NIRB hereby requests that the responsible Minister extend the period for the submission of the Board’s written report for the screening of this project proposal, NIRB File No. 18TN035.

On May 23, 2019 the NIRB requested that the Proponent complete the online application form through the NIRB’s public registry system and ensure, pursuant to s. 144(1) of the NuPPAA, that the information provided be sufficient to determine the scope of the project activities being proposed and that sufficient information has been provided to commence screening.  On May 30, 2019 the NIRB followed up with the Proponent requesting an online application and on June 7, 2019 the NIRB received the required additional information and commenced the screening pursuant to Part 3 of the NuPPAA.  On June 13, 2019 the NIRB distributed notice of the project proposal to potentially affected communities and interested parties with a request for comments to be submitted for the Board’s consideration by July 4, 2019.

Due to the high volume of screenings and other assessments currently before the Board, and in recognition of the time required to translate documents for the Board to evaluate the proposal, the NIRB is unable to provide its written report for the screening of this project proposal within the 45 days as set out in the NuPPAA and additional time is requested to complete the decision-making for this file.  The NIRB anticipates that the screening of this project proposal will be completed by July 31, 2018 at which time a screening decision report will be submitted to the responsible Ministers for consideration; should any additional time be required to conclude the screening process, the NIRB commits to providing further updates as deemed appropriate.

If this request is approved, NIRB understands that the Minister will notify the Proponent and the NIRB of the extension.

All documents received and pertaining to the NIRB’s screening of this project proposal can be accessed from the NIRB’s online public registry at www.nirb.ca/project/125470.

If you have any questions or require clarification regarding this request, please contact our office toll free at 1-866-233-3033.

Sincerely,

<original signed by>

Ryan Barry

Executive Director

Nunavut Impact Review Board

cc:	Karin Strand, Hurtigruten AS

Honourable David Joanasie, Minister of Culture and Heritage, Government of Nunavut

Honourable David Akeeagok, Minister of Economic Development and Transportation, Government of Nunavut

Stanley Anablak, President, Kitikmeot Inuit Association

P.J. Akeeagok, President, Qikiqtani Inuit Association

Geoff Clark, Kitikmeot Inuit Association

Tannis Bolt, Kitikmeot Inuit Association

Stephen Williamson-Bathory, Qikiqtani Inuit Association

Salamonie Shoo, Qikiqtani Inuit Association

Joel Fortier, Qikiqtani Inuit Association

Alexander Stubbing, Culture and Heritage, Government of Nunavut

Sylvie LeBlanc, Culture and Heritage, Government of Nunavut

Jody Kusugak, Economic Development and Transportation, Government of Nunavut

Lisa Pirie-Dominix, Canadian Wildlife Services

Transport Canada