## Sheet1
NIRB File No: 11MN034 |  | Project name: Meliadine Gold Mine Project |  | Project Certificate No. 006, Amendment 02 |  | Parties' Comments
TC No. | Term and Condition Summary | Responsible Parties / Authorities | Associated Plan(s) | Proponent Submission or Summary | Reference (Annual Report) | CIRNAC | DFO | ECCC | HC | TC | KivIA | GN | SDFN NDFN | Proponent's Repsonse
1 | Update Air Quality Monitoring Plan | Agnico Eagle | • Air Quality Monitoring Plan (NIRB Doc ID 354009) • Terrestrial Environment Management and Monitoring Plan (TEMMP) (NIRB Doc ID 354044) | Air Quality Monitoring Plan was updated as required. | 2025 Annual Report, section 7.8.1 and related Appendix 24 2025 Air Quality Monitoring Report |  |  | ECCC-2: 2025 Air Quality Monitoring Report, Appendix A-starting on the second page of Table 1, the solar radiation values in the top row of each page are reported as 0.0 W/m² (with one exception) while adjacent values are well above zero, suggesting a tabulation error. Recommendation: review the solar radiation data in Table 1 of Appendix A to either rule out a tabulation error or enter corrected values for the top row of each page.
2 | Emissions monitoring | Agnico Eagle | Air Quality Monitoring Plan (NIRB Doc ID 354009) | SO₂ and NO₂ emissions monitoring continued in 2025. Results remained within regulatory guidelines and FEIS predictions, with no exceedances reported. | 2025 Annual Report, section 7.8.1 and related Appendix 24 2025 Air Quality Monitoring Report
3 | Dust management and monitoring | Agnico Eagle | Dust Management Plan (NIRB Doc ID 354014) | The Dust Management Plan was updated. | 2025 Annual Report, section 7.8.1 and related Appendix 24 2025 Air Quality Monitoring Report
4 | Incineration Management Plan | Agnico Eagle | Incineration Management Plan (NIRB Doc IDs 354021 and 354023) | The Incineration Management Plan is implemented. | 2025 Annual Report, section 5.2 Appendix 14 2025 Stack Testing Report
5 | Stack testing results | Agnico Eagle |  | Stack testing results are reported annually through the Annual Report. | 2025 Annual Report, section 5.2 Appendix 14 2025 Stack Testing Report |  |  | ECCC-1: Stack testing of the Ketek Incinerator shows dioxin/furan concentrations slightly exceed, on average, the applicable standard. Appendix 14, Appendix B shows details of the three test results for the various parameters; however, only an average of total toxic equivalency for the three tests is provided; the two largest contributors (2,3,4,7,8-Penta CDF and 2,3,4,6,7,8-Hexa CDF) varied substantially across tests. Given differences in temperatures, oxygen levels, and draft values, per-test variation may help diagnose the exceedance. Recommendation: provide total toxic equivalencies for dioxins and furans for each of the three tests, plus insights into the causes of the exceedances. |  |  | KivIA 07 : Dioxins and Furans from the Ketek Incinerator exceed (i.e. 82.2) the applicable CCME limit of 80 TEQ/Rm³. The report documents sporadic oxygen values, lower temperature in the second chamber, negative draft pressure and inadequate retention time in the secondary chamber; All factors which led to poor combustion of volatile compounds. In addition, issues noted in Appendix G relate to improper sorting of waste, lack of a good mix of combustible materials, lack of clear guidance, limited feedback on segregation errors and SOP non-compliance leading to equipment damage. Several solutions were recommended but their effectiveness cannot be confirmed for 12 months. Request: Although several solutions were recommended the KivIA would like to see a quarterly update on whether the recommended solutions are actually lowering the Dioxins and Furans exceedances. In addition, the external consultants should also complete testing during winter conditions in order to determine if there are any differences in stack emissions between summer and winter conditions and if the solutions suggested for summer conditions are rigorous enough for winter conditions.
6 | Dust suppression measures at landfill | Agnico Eagle | • Dust Management Plan (NIRB Doc ID 354014) • Landfill and Waste Management Plan (NIRB Doc ID 354034) | The Dust Management Plan and Landfill and Waste Management Plan are in place and implemented. | 2025 Annual Report, section 5.1
7 | Calculations of greenhouse gas (GHG) emissions generated by the Project | Agnico Eagle |  | 2024 GHGRP and OBPS reports were submitted to ECCC on June 2nd, 2025 as required. 2025 GHGRP and OBPS reports will be submitted to ECCC by June 1st, 2026 and shared with the NIRB. | 2025 Annual Report, section 7.8.2
8 | Engage Inuit in initiatives related to climate change | Agnico Eagle |  | No climate change study or research occurred in 2025.
9 | Greenhouse Gas (GHG) Emissions Reduction Plan | Agnico Eagle | Greenhouse Gas Emissions Reduction Plan (NIRB Doc ID 323966) | The Greenhouse Gas Emissions Reduction Plan is implemented. | 2025 Annual Report, section 7.8.2
10 | Noise and Vibration Abatement Plan | Agnico Eagle GN ECCC HC | • Noise Abatement and Monitoring Plan (NIRB Doc ID 354031) • Blast Monitoring Program (NIRB Doc ID 354010) • Terrestrial Environment Management and Monitoring Plan (TEMMP) (NIRB Doc ID 354044) | The Noise Abatement and Monitoring Plan is implemented. No substantial changes in mine activity occurred in 2025 and sound levels are being monitored. | 2025 Annual Report Sections 7.6 and 7.7 and related appendices (Appendix 23 2025 Noise Monitoring Report and Appendix 22 2025 Blast Monitoring Report) |  |  |  | Clearer reporting on noise data limitations and source attribution would support interpretation of exceedances and long-term review of potential community exposure. Please see HC-02 for details. HC-02: Measured 24-hour Leq values exceeded FEIS predictions at NPOR006a, NPOR008, and NPOR017a in 2025, and exceeded the noise monitoring criterion at NPOR008 and NPOR017a. Sound recordings were not available in 2025, limiting source attribution and secondary filtering. Exceedances were attributed to likely factors (elevated wind, helicopter overflights, nearby mine activity, one short-duration intense event at NPOR017a) but sources could not be confirmed; AEM concludes higher Leq values are more likely related to data-processing limitations than an actual increase in mine-related sound. Request: Health Canada requests that future annual reports clearly describe noise data limitations, source attribution considerations, including the availability of sound recordings, and the interpretation of exceedances relative to potential community exposure. Where exceedances are attributed to non-routine or non-representative sources, confirmed and inferred sources should be clearly identified, and the interpretation of the results for long-term noise monitoring and community well-being considerations explained. |  | KivIA 09: Sound recording was not used during 2025 to screen out data peaks, limiting the ability to pick up potential sound impacts from the saline waterline and additional open-pit mining activities at the Pump Zone. Request: re-implement sound recording in 2026. | The Government of Nunavut (GN) notes that Agnico Eagle Mines Limited’s (Agnico; AEM; Proponent) 2025 annual report materials lack key information required for the GN to assess compliance with. this Term and Condition (TC) and the associated management plans. GN #01: The 2025 annual report materials lack key information needed to assess compliance with the Noise Abatement and Monitoring Plan (NAMP) and the TEMMP. The NAMP references the TEMMP for measures to minimize aircraft noise impacts on wildlife, including flight heights (TEMMP s.6.1.4; Fig.13) and helicopter usage restrictions (TEMMP s.4.5.3). Aside from Table 21 (Blast Events and Helicopter Use in relation to the 2025 caribou pre-calving migration period), very little information demonstrates compliance, mirroring last year's issue. Request: provide maps and information detailing flight paths, flight length, and flight height (m) for 2025 and in future annual reports so the GN can assess compliance with the TEMMP. Request: The GN requests that the Proponent provide maps and other information detailing flight paths, flight length and flight height (m) for 2025 and in future annual reports so the GN can assess the Proponent’s compliance with the TEMMP.
11 | Noise and vibration monitoring at accommodation sites | Agnico Eagle | • Noise Abatement and Monitoring Plan (NIRB Doc ID 354031) • Blast Monitoring Program (NIRB Doc ID 354010) | In response to comments from Health Canada, Agnico Eagle conducted indoor noise monitoring in off-duty worker sleeping quarters at the Meliadine Mine. Results were reported in the 2024 Annual Report and showed noise levels generally aligned with the WHO guidelines. Mitigation measures are in place. | 2024 Annual Report Section 7.7.2 (Indoor Noise Monitoring) (NIRB Doc ID 353952)
12 | Conduct permafrost mapping and monitoring | Agnico Eagle |  | Permafrost mapping and monitoring are completed as required. The Annual Geotechnical Inspection report includes clear commentary on permafrost status throughout the various mine site areas. | 2025 Annual Report Section 4.1.9 and related Appendix 6 (2025 Annual Geotechnical Inspection)
13 | Undertake geotechnical investigations to minimize impacts on sensitive landforms | Agnico Eagle | Environmental Management and Protection Plan (NIRB Doc ID 354038) | Required geotechnical investigations are conducted. Maintenance is completed where needed and mitigations measures are in place. | 2025 Annual Report Section 4.1 and related Appendices 6 (2025 Annual Geotechnical Inspection), Appendix 7 and 8 2025 Annual Geotechnical Report Agnico Eagle Reponses and Action Table)
14 | Conduct thermal analysis to support dike and Tailings Storage Facility design | Agnico Eagle |  | Thermal and geotechnical assessments are completed to support the design of the dikes and the TSF. Results are provided in the Annual Report. | 2025 Annual Report Section 4.1 and related Appendix 6 (2025 Annual Geotechnical Inspection)
15 | Assess the potential environmental effects of a post-closure failure of the geomembrane of the Tailings Storage Facility while tailings are in a thawed state | Agnico Eagle | • Risk Management and Emergency Response Plan (NIRB Doc ID 354033) • Interim Closure and Reclamation Plan (ICRP) (NIRB Doc IDs 354025 and 354027) | Progressive reclamation of the TSF continued in 2025 as per the ICRP. The Risk Management and Emergency Response Plan covers failure scenarios. | 2025 Annual Report Section 8
16 | Finalize and implement an Erosion Management Plan | Agnico Eagle | • Water Management Plan (NIRB Doc ID 354045) • Sediment and Erosion Management Plan (NIRB Doc ID 354039) | The Sediment and Erosion Management Plan is in place and implemented. | 2025 Annual Report Section 7.5 |  | DFO would like to bring to the proponents attention that there is a new interim standard for Planning for Land-Based Erosion and Sediment Control. It can be found at: https://www.dfo-mpo.gc.ca/pnw-ppe/standards-normes/erosion-sediment-eng.html
17 | Monitor permafrost integrity | Agnico Eagle |  | See T&C12. | 2025 Annual Report Section 4.1.9 and related Appendices 6 (2025 Annual Geotechnical Inspection), Appendix 7 and 8 2025 Annual Geotechnical Report Agnico Eagle Reponses and Action Table)
18 | As-built drawings and final design plans | Agnico Eagle |  | Submitted as-built reports and drawings can be found on the NWB public registry (https://public.nwb-oen.ca/). | 2025 Annual Report Section 2.1.2
19 | Monitor thermal and structural condition of Tailings Storage Facility and Waste Rock Storage Facility | Agnico Eagle | Mine Waste Management Plan (NIRB Doc ID 354029) | The Mine Waste Management Plan is implemented. Results of the monitoring program are presented in the Annual Report. | 2025 Annual Report Section 4.1 and related Appendix 6 (2025 Annual Geotechnical Inspection)
20 | Closure and Reclamation Plan | Agnico Eagle | Interim Closure and Reclamation Plan (ICRP) (NIRB Doc IDs 354025 and 354027) | The ICRP will be updated as further reclamation knowledge is gained. | 2025 Annual Report Section 8
21 | Waste Management Plan for Project landfills. | Agnico Eagle | Landfill and Waste Management Plan (NIRB Doc ID 354034) | The Landfill and Waste Management Plan is implemented. | 2025 Annual Report Section 5.1
22 | Report on adaptations to the Mine Waste Management Plan and practices based on results obtained through monitoring | Agnico Eagle | Mine Waste Management Plan (NIRB Doc ID 354029) | The updated Mine Waste Management Plan was submitted in Appendix of the Annual Report. | 2025 Annual Report, Appendix 28 | CIRNAC #3-By end of 2025, tailings placement totaled 1,272,000 m³ (2,098,000 t) with remaining design capacity of 654,000 m³ (1,079,000 t). The Mine Waste Management Plan shows ~15.6 Mt of additional tailings over six more years, with 1,760,000 t planned for the dry stack in 2026 alone — exceeding remaining design capacity by more than 681,000 t. The 2025 Annual Report is silent on how AEM intends to store these tailings and the implications of the ~1.6 times expansion. Request: AEM provide a summary discussion of its plans for expanding the approved TSF capacity to full life of mine tailings deposition capacity, contingency storage availability, and the schedule/technical basis for future tailings storage expansion given the limited remaining capacity of approximately 654,000 m³ and significant additional capacity requirement. CIRNAC #4-Waste rock from the open pits is used for construction of infrastructure. During construction, a sampling program is conducted to ensure that only rock classified as non-Potentially Acid Generating (non-PAG) is used in the construction. Yet 2024–2025 sampling returned some PAG/Uncertain samples (2024: one Uncertain from Pump Road; 2025: two Uncertain and two PAG). Follow-up 2025 sampling on the 2024 Pump Road Uncertain result found a ~20 m section (1+170m to 1+190m) containing PAG material, which AEM indicates will be removed at closure. It is unclear how PAG/Uncertain material came to be used in construction. Request: a) Provide clarification regarding the identification of PAG/Uncertain construction materials associated with Pump development infrastructure and the proposed long-term management strategy, including confirmation of whether additional similar materials may remain unidentified within operational infrastructure. b) Provide clarification on why the material was mis-characterized and what changes to the management plans have been implemented to prevent similar issues occurring in the future. |  |  |  |  | KivIA 06: In the Annual Report, section 2.1.3 the tonnes of ore extracted from the Pump 01 and Pump 02 open pits is reported as 561,000 tonnes for each open pit. Table 3.2 in the OSMP (Appendix 28-6) reports the tonnes of ore extracted from the Pump 01 as 146,736t and Pump 02 as 23,280t, respectively, which are 73% and 96% lower than in the Annual Report text. Request: The KivIA requires the correct numbers be put into the Annual Report or the OSMP.
23 | Mine Waste Management Plan – Discovery Deposit | Agnico Eagle NRCan | ARD/ML Sampling and Testing Plan | Not Yet Active/Not Yet Applicable
24 | Collect data to better define vertical and horizontal groundwater flow | Agnico Eagle | Groundwater Management Plan (NIRB Doc ID 354018) | Report submitted in Q4, 2016. (NIRB Doc ID 305733 through 305769) The Groundwater Management Plan is implemented, which includes monitoring.
25 | Develop a Groundwater Management Plan with adaptive management strategies for management of saline groundwater | Agnico Eagle KivIA ECCC DFO GKD | • Groundwater Management Plan (NIRB Doc ID 354018) • Adaptive Management Plan for Water Management (NIRB Doc ID 354049) | The Management Plans were submitted and are implemented. | 2025 Annual Report Sections 3.1 and 3.2 | CIRNAC #1-The waterline commissioning schedule has shifted across annual reports; Planned activities for 2026 now include minor construction, hydrotesting, and commissioning. There are inconsistencies among report sections on when waterline/WES02 discharge begins. Request: (1) Provide an assessment of risks associated with delayed commissioning of the saline discharge waterline, including implications for TIRI02/WES02 storage capacity, saline water quality evolution, and long-term dependence on interim onsite storage and treatment systems. 2. Clarify the status of the waterline and provide additional details on: a) Planned 2026 and 2027 construction and commissioning activities, b) Schedules for the start of saline water and contact water discharge at Itivia, and c) Expected operational practices (daily, monthly, annual discharge) upon start of discharge at Itivia. CIRNAC #2- The 2025 Annual Report introduces a significant change: rather than dewatering TIRI02 via marine discharge at Itivia upon waterline completion, saline contact water will be stored in TIRI02 (max ~1.29 Mm³) before transfer to WES02 over 2027–2029. It is unclear why TIRI02 water is transferred to WES02 rather than pumped to and treated at the Saline Effleunt Treatment Plant – Water Treatment Complex (SETP-WTC) and discharged after treatment at Itivia. TIRI02 has been used for sludge disposal since 2021, and future sludge practices are unclear. Request: a) Provide a detailed discussion on the rationale and basis for TIRI02 water transfer to WES02 instead of drawdown via pumping to the SETP-WTC and discharge at Itivia. b) Provide details on when discharge of saline water from WES02 is expected to begin and the expected rate of discharge. c) Provide details on changes to sludge management and disposal practices that will occur as a result of dewatering TIRI02 and use of WES02 for saline water storage. | The Groundwater Management Plan and the Adaptive Management Plan for Water Management, were previously submitted and are being implemented. No updates were reported this year. DFO has no comments. | ECCC-8: The saline effluent treatment plant (SETP) is scheduled to be commissioned in 2026. WMP v16 stated 'Agnico Eagle is currently designing a treatment system for ammonia nitrogen to meet the MDMER,' which no longer appears in v17. Recommendation: provide an update on the methods chosen to treat ammonia at the saline effluent treatment plant. |  |  |  |  | No additional comments.
26 | Analyze pit refill rates | Agnico Eagle | • Water Management Plan (NIRB Doc ID 354045) • Groundwater Management Plan (NIRB Doc ID 354018) | The Water Balance and Water Quality Model is updated as per the Water Management Plan. |  | CIRNAC #2- The 2025 Annual Report introduces a significant change: rather than dewatering TIRI02 via marine discharge at Itivia upon waterline completion, saline contact water will be stored in TIRI02 (max ~1.29 Mm³) before transfer to WES02 over 2027–2029. It is unclear why TIRI02 water is transferred to WES02 rather than pumped to and treated at the Saline Effleunt Treatment Plant – Water Treatment Complex (SETP-WTC) and discharged after treatment at Itivia. TIRI02 has been used for sludge disposal since 2021, and future sludge practices are unclear. Request: a) Provide a detailed discussion on the rationale and basis for TIRI02 water transfer to WES02 instead of drawdown via pumping to the SETP-WTC and discharge at Itivia. b) Provide details on when discharge of saline water from WES02 is expected to begin and the expected rate of discharge. c) Provide details on changes to sludge management and disposal practices that will occur as a result of dewatering TIRI02 and use of WES02 for saline water storage.
27 | Update Aquatic Effects Monitoring Plan (AEMP) including surface water, snowpack and dustfall monitoring | Agnico Eagle | • Aquatic Effects Monitoring Program (AEMP) Design Plan (NIRB Doc IDs 354048 and 354050) • Air Quality Monitoring Plan (NIRB Doc ID 354009) | The AEMP Design Plan was updated and monitoring results are presented in the Annual Report. | 2025 Annual Report sections 7.1 and 7.8 related appendices (Appendix 18 2025 AEMP Report and Appendix 24 2025 Air Quality Monitoring Report) |  |  | ECCC-3: Measured ammonia and phosphorus in containment pond CP1 were again below model predictions. Investigation into the discrepancy between modelled and measured concentrations of these nutrients was initiated in 2023. The assessment concluded that natural attenuation by algal growth played a role, but the mechanism was not fully understood. Further work is reported in the 2025 Annual Report: “Work to implement a second prediction for ammonia and phosphorous within the WBWQM [Water Balance and Water Quality Model], which will include a limited calibration that will better reflect the natural attenuation process in CP1, is still ongoing. An understanding of the processes affecting ammonia and phosphorus concentrations in CP1 could contribute to a better understanding of the fate of these nutrients in the receiving environment. Recommendation: provide a timeline for the second prediction of CP1 ammonia and phosphorus concentrations in the WBWQM. ECCC-5: An update to the AEMP Action Level for phosphorus is proposed based on the CCME guidance framework. The approach is reasonable but needs clarification: the measurements/statistics used to assess change relative to the Normal Range (0.006 mg/L) have not been specified, and it is unclear whether sufficient samples are collected per station to calculate an accurate 90th percentile. It is also unclear which trigger values will apply (whether the CCME 50% increase will be adopted as the AEMP benchmark, and whether the Low Action Level at 75% of benchmark would include a 37.5% increase). Recommendation: clarify how they propose to implement the CCME guidance framework for phosphorous in the AEMP, including what annual values or statistics they will compare with the Normal Range, and the proposed AEMP benchmark and Low Action Level. |  |  | KivIA 10: KivIA has received reports from Rankin Inlet community members of anomalous turbidity and algal growth in the south basin of Meliadine Lake, corroborated by AEMP productivity studies; other regional lakes do not show similar trends. Total phosphorus at MEL-01 exceeded the AEMP Action Level (0.0075 mg/L) in 6 of 18 open-water samples, with July–September mean of 0.0077 mg/L and at least one exceedance of the AEMP Benchmark (0.01 mg/L); some values exceed the CCME 50%-above-baseline (0.009 mg/L) threshold. Request: continue to monitor total phosphorus concentrations in Meliadine Lake following commissioning of the waterline to Itivia Harbour. Should prioritized discharge in the Adaptive Management Plan fail to address these increasing total phosphorous concentrations, Agnico Eagle should explore other mechanisms to limit nutrient loading into Meliadine Lake. KivIA 11: The structured reference-lake monitoring program began in 2025 as a three-year study and acknowledges the dataset is limited/semiquantitative. Yet the report interprets differences between 2021, 2024, and 2025 as temporal change/regional trends, though 2021 and 2024 data were collected under separate (EEM) programs and cannot reliably be combined. This matters because reference-lake data support broader conclusions on regional drivers (e.g., copper); treating non-comparable datasets as temporal change may overstate regional trends and reduce ability to distinguish mine-related effects. Request: interpretation of temporal trends at the reference lakes be deferred until sufficient data are collected under the structured monitoring program (i.e., completion of the three‑year study in 2027), and that interim results be presented as discrete observations with clear acknowledgement of associated uncertainties and limitations. KivIA 12: Copper in 2025 exceeded the historical Normal Range (~0.86 µg/L) across multiple areas of Meliadine Lake, reaching 1.34 µg/L at MEL-01 and 1.67 µg/L at MEL-02 (~56% and ~94% above baseline); comparable elevations occurred at reference areas and Itiqlak (Atulik) Lake. Reference datasets are limited and do not yet robustly distinguish regional trends from mine-related contributions, and increases are larger at MEL-01/02 than MEL-04/05. As such, mine-related inputs are a plausible contributing source and the increase should not be taken as the normal range. Request: evaluation of copper in Meliadine Lake be strengthened through improved presentation, analysis, and interpretation of available data, once available. In the interim, the KivIA recommends that Agnico Eagle continue to monitor copper concentrations in Meliadine Lake following commissioning of the waterline to Itivia Harbour.
28 | Sediment and Erosion Management Plan | Agnico Eagle | • Water Management Plan (NIRB Doc ID 354045) • Sediment and Erosion Management Plan (NIRB Doc ID 354039) | See T&C16. | 2025 Annual Report Section 7.5
29 | Monitor and maintain culverts and other water infrastructure | Agnico Eagle | • Water Management Plan (NIRB Doc ID 354045) • Freshet Management Plan (NIRB Doc ID 354036) • Roads Management Plan (NIRB Doc ID 354037) | Monitoring and maintenance is performed as per the Management Plans. Replacement of infrastructure is reported on in the Annual Report. | 2025 Annual Report Section 2.2.1 |  | Future culvert installations for fish bearing water crossings will require design for fish passage and long term physical stability. DFO will require a request for review for these crossings along with the designs. DFO completed a July 2025 site visit at the Meliadine Project. The site was found to be largely compliant. DFO noted gravel build-up at bridges along the AWAR; the Proponent quickly updated its road maintenance plan to mitigate. | ECCC-7: The list of water management systems in WMP v17 changed from v16 without full explanation. Water retention dikes D-B5North and D-B5South were removed and D-DCP1 and D-DCP5 added (unclear if renamed or no longer needed); dewatered waterbody B59 was removed and B34 added (unclear if B59 no longer needs dewatering). Recommendation: clarify the removal of dikes D-B5North and D-B5South and dewatered waterbody B59 from the list of water management systems.
30 | Aquatic Effects Monitoring Plan (AEMP) to include, at a minimum info related to reference lakes, sedimentation, and fish tissue testing | Agnico Eagle | Aquatic Effects Monitoring Program (AEMP) Design Plan (NIRB Doc IDs 354048 and 354050) | The AEMP Design Plan was updated and monitoring results are presented in the Annual Report. | 2025 Annual Report section 7.1 and related appendix (Appendix 18 2025 AEMP Report) |  | Hydrologic monitoring of water levels in Meliadine Lake, and flows at the 2 outlets of Meliadine Lake, began late in the open water season of 2024. Following the 2024 annual report review, AEM stated they were developing a water balance model for the Meliadine Lake, and additional information would be included in the next update of the Water Quality and Flow Monitoring Plan and reported in the annual Report. The 2025 Annual Report did not contain an updated Water Quality and Flow Monitoring Plan or information on this hydrological monitoring. It remains unclear how this information will be reported and incorporated into the overall environmental management system in place at the Meliadine Mine. It is common place for a mine's Aquatic Effects Management Program (AEMP) to include a hydrological component, which also allows for regular evaluation and potential response actions if detrimental effects are observed. DFO would ultimately like to better understand some of the details of this monitoring program, including: • what historical data is available and will be used for long term comparison, • how this will be incorporated into the overall environmental management program, and • how mine related changes in water level will be responded to if determined to be detrimental to fish or fish habitat. | ECCC-4: The title of Table 2-5 suggests dissolved organic carbon (DOC) data will be included, but DOC data are not presented nor discussed, even though DOC appears to have been measured in 2025 (Appendix C1). DOC is sensitive to permafrost degradation in the catchment; analyzing DOC trends could improve understanding of regional water quality change. Recommendation: present a summary of DOC concentrations in Atulik Lake, Peter Lake, and Meliadine Lake reference areas since the late 1990s and discuss the results, or explain why it is not possible. ECCC-6: Mine influence on peninsula lakes B7 and A8 has been an ongoing concern. In 2025 arsenic concentrations in Lake B7 continued to increase and are now above the site-specific water quality objective in four of five months sampled; the annual rate of increase rose (26% from 2023 to 2024; 41% from 2024 to 2025). The AEMP Report concludes “Year-over-year increases in arsenic suggest the TSF [tailings storage facility] as the primary source, although regional climate-driven processes are likely also a factor based on temporal trends observed at the regional reference lakes.” Although Lake B7 will eventually be dewatered (planned 2027), the arsenic migration pathway from the TSF will persist and could affect the downstream environment. Recommendation: discuss how the TSF is contributing to increasing concentrations of arsenic in Lake B7 and propose measures to mitigate the source of arsenic. | HC-02: Integration of arsenic trends across environmental media would help inform ongoing arsenic management, mitigation, and monitoring. The AEMP reports increasing arsenic in Lake B7 (exceeding the AEMP Action Level in all 2025 samples), suggesting the TSF as the source with some regional climate contribution; Meliadine Lake remained below drinking-water and aquatic-life guidelines. The TEMMP soil/vegetation program assessed arsenic across soil, leaves, berries, lichen, and snow, with some media showing decreases with distance from the Mine/AWAR. Because arsenic findings are spread across separate programs, it is unclear how aquatic, terrestrial, snow, and air/dust results are evaluated collectively to determine whether trends are localized, natural, or project-related, and whether follow-up on exposure pathways (e.g., country foods) is warranted. Request: integrate arsenic-specific findings from the AEMP, TEMMP, and air/dust monitoring programs in the 2026 Annual Report to support a fuller review and determine whether changes warrant additional human-health consideration.
31 | Maintain setback distance between project quarries and fish-bearing or permanent water bodies | Agnico Eagle | Borrow Pits and Quarries Management Plan (NIRB Doc ID 353968) | As per the Borrow Pits and Quarries Management Plan, a setback of 31 m from waterbodies will be maintained when practicable. | 2025 Annual Report Sections 4.2, 7.4 and 7.5, related appendix (Appendix 9 2025 Metal Leaching and Acid Rock Drainage Report) | CIRNAC #4-Waste rock from the open pits is used for construction of infrastructure. During construction, a sampling program is conducted to ensure that only rock classified as non-Potentially Acid Generating (non-PAG) is used in the construction. Yet 2024–2025 sampling returned some PAG/Uncertain samples (2024: one Uncertain from Pump Road; 2025: two Uncertain and two PAG). Follow-up 2025 sampling on the 2024 Pump Road Uncertain result found a ~20 m section (1+170m to 1+190m) containing PAG material, which AEM indicates will be removed at closure. It is unclear how PAG/Uncertain material came to be used in construction. Request: a) Provide clarification regarding the identification of PAG/Uncertain construction materials associated with Pump development infrastructure and the proposed long-term management strategy, including confirmation of whether additional similar materials may remain unidentified within operational infrastructure. b) Provide clarification on why the material was mis-characterized and what changes to the management plans have been implemented to prevent similar issues occurring in the future.
32 | Site Drainage and Silt Control Plan | Agnico Eagle | • Water Management Plan (NIRB Doc ID 354045) • Sediment and Erosion Management Plan (NIRB Doc ID 354039) • Roads Management Plan (NIRB Doc ID 354037) | Plans are in place to manage drainage and sedimentation.
33 | Meet or exceed guidelines set by Fisheries and Oceans Canada for blasting | Agnico Eagle | Blast Monitoring Program (NIRB Doc ID 354010) | Blasting activies are monitored as per the Blast Monitoring Program. In 2025, no exceedances were observed. | 2025 Annual Report Section 7.6 and related Appendix 22 2025 Blast monitoring report
34 | Watercourse infrastructure shall not prevent or limit fish passage | Agnico Eagle | • Water Management Plan (NIRB Doc ID 354045) • Roads Management Plan (NIRB Doc ID 354037) | Culvert replacements are discussed in the Annual Report. | 2025 Annual Report section 2.2.1
35 | Minimize Project footprint | Agnico Eagle |  | Direct habitat loss was last assessed in 2024 (Appendix 26 2024 TEMMP Report) at 696 ha (NIRB Doc IDs 353998, 353999, 354001 and 354003). The next assessment will be in 2027. | 2025 Annual Report Section 7.9 and related Appendix 25 2025 TEMMP Report
36 | Invasive species – vehicle inspections | Agnico Eagle |  | Equipment and cargo are inspected before shipping. | 2025 Annual Report Section 7.9 and related Appendix 25 2025 TEMMP Report
37 | Monitoring for invasive species | Agnico Eagle | Terrestrial Environment Management and Monitoring Plan (TEMMP) (NIRB Doc ID 354044) | Inavsive species monitoring is completed as per the TEMMP and reported on in the Annual Report. | 2025 Annual Report Section 7.9 and related Appendix 25 2025 TEMMP Report
38 | Monitor metal concentrations in vegetation | Agnico Eagle | Terrestrial Environment Management and Monitoring Plan (TEMMP) (NIRB Doc ID 354044) | Baseline soil and vegetation monitoring began in 2017. Follow-up assessments were conducted every 3 years (2019, 2022, 2025) as per the TEMMP. | 2025 Annual Report Section 7.9, and related appendix (Appendix 25 2025 TEMMP Report)
39 | Monitor distribution, abundance and health of vegetation | Agnico Eagle | Terrestrial Environment Management and Monitoring Plan (TEMMP) (NIRB Doc ID 354044) | Vegetation health is monitored every 3 years as per the TEMMP. Results of the last assessment (2025) are included in the 2025 Annual Report. | 2025 Annual Report Section 7.9, and related Appendix 25 2025 TEMMP Report
40 | Review all monitoring information and the vegetation mitigation and management plans developed under its Environmental Management Plan and Terrestrial Environment and Monitoring Plan (TEMMP) | Agnico Eagle | Terrestrial Environment Management and Monitoring Plan (TEMMP) (NIRB Doc ID 354044) | Monitoring data is reviewed on an annual basis and management plans are updated as needed. Vegetation health is monitored every 3 years as per the TEMMP. | 2025 Annual Report Section 7.9.1 and related Appendix 25 2025 TEMMP Report
41 | Develop a progressive revegetation program for disturbed areas that are no longer required for operations | Agnico Eagle |  | Tundra Restoration and Natural Recovery Monitoring study was completed and reported on in the 2021 Annual Report. Future updates of the ICRP will include results from research projects and Inuit Qaujimajatuqangit (IQ), as applicable. | 2021 Annual Report section 7.9, section 8 and related appendix (2021 Tundra Restoration and Natural Recovery Monitoring Technical Report) (NIRB Doc ID 338868)
42 | Include re-vegetation strategies in its Closure and Reclamation Plan that support progressive reclamation and that promote natural revegetation | Agnico Eagle |  | Not Yet Active / Not Yet Applicable Revegetation strategies will be further discussed in a future update of the ICRP and in the Final Closure and Reclamation Plan. | 2021 Annual Report section 7.9, section 8 and related appendix (2021 Tundra Restoration and Natural Recovery Monitoring Technical Report). (NIRB Doc ID 338868)
43 | Develop and implement Project-specific monitoring for the terrestrial environment through Terrestrial Environment Management and Monitoring Plan (TEMMP) | Agnico Eagle | Terrestrial Environment Management and Monitoring Plan (TEMMP) (NIRB Doc ID 354044) | The TEMMP (V5) was updated and submitted with the 2024 Annual Report, including baseline information on caribou calving grounds and revised monitoring and mitigation protocols, including Level 4 mitigation and road closure triggers. | 2024 Annual Report Section 11.11 and related appendix (Appendix 38 2024 TAG Annual Report) (NIRB Doc ID 354022) | [5 empty] | The KivIA attended the TAG meetings in early 2025 and provided comments to support Agnico Eagle and the TAG's efforts to reach sufficient agreement to submit an updated TEMMP vs 5.0 to NIRB in March 2025.The KivIA notes that the TAG's function includes reviewing the effectiveness of measures (TEMMP S.1.4.2). The KivIA has questions about how effectiveness was addressed in the 2025 Annual Report - see Effects Monitoring Comment KivIA 04. KivIA 04: The KivIA does not agree that the TEMMP vs. 5.0 was completely applied to the 2025 monitoring activities. 2025 revised TEMMP vs 5.0 includes mitigation effectiveness as a monitoring objectives for calving range (S.4.2.2), behavior monitoring (S. 4.2.4) and the cameras (S.4.2.5) but it is not specified how effectiveness was addressed in the 2025 Annual Report. KivIA requests that Agnico Eagle implement the TEMMP vs. 5.0 objectives referencing mitigation effectiveness for the annual caribou monitoring program.
44 | Develop a Caribou monitoring program. Revise the 2021 Technical Memorandum “Collared Caribou Meliadine AWAR Interactions” | Agnico Eagle GN | Terrestrial Environment Management and Monitoring Plan (TEMMP) (NIRB Doc ID 354044) | Agnico Eagle submitted multiple analyses and reports in support of T&C44 compliance (Golder 2022, WSP 2023a, 2023b, 2023c and 2024). The caribou monitoring program is continuously improved through the TAG. The updated TEMMP (V5) was submitted with the 2024 Annual Report. | 2024 Annual Report Section 7.9, 11.1 and related appendices (Appendix 26 2024 TEMMP Report, Appendix 38 2024 TAG Annual Report) (NIRB Doc IDs 353998, 353999, 354001, 354003 and 354022) | [5 empty] | The KivIA provided detailed reviews of the Com. 38 analyses and appreciates Agnico Eagle attempts to address the technical comments. The KivIA does not fully support the analyses given the low sample size of the number of collared caribou and the role of insect harassment(TAG minutes March 2025). | The GN has no comments regarding this TC at this time.
45 | Cooperate with existing and planned regional and/or community-based monitoring programs for terrestrial wildlife and habitat, especially regional studies of Qamanirjuaq caribou | Agnico Eagle |  | The Data and Sample Sharing Agreement was signed with the Government of Nunavut in March 2023. | 2025 Annual Report Section 7.9, 11.1 and related appendices (Appendix 25 2025 TEMMP Report, Appendix 37 2025 TAG Annual Report) | [5 empty] | The KivIA notes that the 2025 Annual Report did not list any regional studies for the Qamanirjuaq herd.
46 | Update Terrestrial Environment Management and Monitoring Plan (TEMMP) for the Project to include a detailed harvest study | Agnico Eagle GN HTOs | Terrestrial Environment Management and Monitoring Plan (TEMMP) (NIRB Doc ID 354044) | Agnico Eagle continues to support a detailed harvest study in collaboration with the Kangiqliniq Hunters and Trappers Organization and other partners. It is included in Appendix of the 2025 TEMMP report. | 2025 Annual Report Section 7.9 and related appendix (Appendix 25 2025 TEMMP Report, which includes the 2025 Hunter Harvest Study Report) | [5 empty] | The KivIA has reviewed the 2025 Harvest Study. Since the AWAR was built, the harvest of caribou within the Local Study Area has increased but not within 5km of the AWAR. This may have implications for caribou responses to the road (App. 25, Table 24). | The GN has no comments regarding this TC at this time.
47 | Share caribou monitoring data with the Government of Nunavut | Agnico Eagle GN |  | The Data and Sample Sharing Agreement was signed with the Government of Nunavut in March 2023. | [7 empty] | The GN has no comments regarding this TC at this time.
48 | Develop a Road Access Management Agreement with monitoring and mitigation measures for caribou harvesting and the increased harvesting access created by the all‑weather road. | Agnico Eagle GN KivIA KWB HTOs | • Roads Management Plan (NIRB Doc ID 354037) • Terrestrial Environment Management and Monitoring Plan (TEMMP) (NIRB Doc ID 354044) | The Roads Management Plan and TEMMP are implemented. Monitoring results and mitigation measures are reported in the Annual Report. | 2025 Annual Report Section 7.9.1 and related appendices (Appendix 25 2025 TEMMP Report, 2025 Caribou Behavior Report, 2025 Caribou Camera Report) | [5 empty] | The KivIA notes that the Annual Report does not comment on any impacts on harvesting relative to the effectiveness of the Road Management Plan. | The GN has no comments regarding this TC at this time.
49 | Ensure proper permitting through Nunavut Research Institute (NRI) | Agnico Eagle NRI |  | No research activities were undertaken that would trigger the requirement for a scientific research licence under the Nunavut Scientists Act.
50 | Develop a strategy for progressive recovery of terrestrial wildlife habitat | Agnico Eagle |  | See T&C41. Tundra Restoration and Natural Recovery Monitoring study was completed and reported on in the 2021 Annual Report. Future updates of the ICRP will include results from research projects and Inuit Qaujimajatuqangit (IQ), as applicable. | 2021 Annual Report section 7.9, section 8 and related appendix (2021 Tundra Restoration and Natural Recovery Monitoring Technical Report) (NIRB Doc ID 338868)
51 | Minimize helicopter disturbance in lqalugaaruup Nunanga Territorial Park | Agnico Eagle | Terrestrial Environment Management and Monitoring Plan (TEMMP) (NIRB Doc ID 354044) | As per the TEMMP, no routine helicopter flights were conducted over or landed in the lqalugaarjuup Nunanga Territorial Park.
52 | Undertake periodic surveys and a habitat assessment for muskoxen in the regional study area by partnering with, or complementing, the existing regional muskox monitoring programs | Agnico Eagle |  | No surveys were completed by the GN in 2025 and in-kind contributions were not requested.
53 | Conduct furbearer den surveys prior to construction | Agnico Eagle | Terrestrial Environment Management and Monitoring Plan (TEMMP) (NIRB Doc ID 354044) | As per the TEMMP, in 2025, Agnico Eagle surveyed for dens of key furbearers before construction. Details are presented in the Annual Report. | 2025 Annual Report Section 7.9.1 and related appendix (Appendix 25 2025 TEMMP Report)
54 | Ensure Project infrastructure does not interfere with movement of Caribou and other terrestrial wildlife | Agnico Eagle | Terrestrial Environment Management and Monitoring Plan (TEMMP) (NIRB Doc ID 354044) | Agnico Eagle ensures roads and waterlines are designed to allow safe movement of caribou and other wildlife. 80-90% of the waterline is covered. | 2025 Annual Report, section 2.1.2 | [5 empty] | KivIA has undertaken visual surveys of the design of the waterline covering and design while noting the lines were not operational. The KivIA has recommendations for veryifying that the design does not impede caribou movements - see Effects Monitoring Comment KivIA 01 KivIA 01: T&C 54 requires waterlines be constructed for safe passage of caribou and other terrestrial wildlife; the issue is whether the design (fine gravel covering) is effective. The 2025 Annual Report does not report caribou exposure or responses to the waterlines and does not specify whether camera placement and AWAR surveys would detect responses. In 2025 the waterline was mostly complete (not operational) and construction did not coincide with caribou migration. Contingency planning for salt-water spills is required. Request: provide details about how the AWAR surveys and cameras will detect caribou responses relative to the waterlines to measure the effectiveness of the design mitigation (fine gravel covering). The KivIA also recommends that track surveys be undertaken to document caribou responses to the waterlines before and during waterline operations. KivIA 05: Traffic frequency information is incompletely reported. KivIA appreciates the remote cameras used to monitor traffic frequency but the reporting needs more detail to examine effects of traffic on caribou. Request: The KivIA requests that details include that average number of detections requires a measure of variability. The average (and variance) should be extrapolated to hourly traffic frequency (passages/minute) to compare traffic during the four levels of mitigation and measure the daily/hourly gaps in traffic. Despite the camera objective to measure traffic, the frequency of traffic is measured as average detection rates rather the more conventional measure of vehicle passages per minute to describe traffic volumes. Details about the passage duration and frequency of convoys for essential traffic during periods of AWAR restriction should be reported. |  | SDFN/NDFN Table 2, Comment 1: (App.28-7, s.10.1/10.2) The wording “If more than 50 caribou are detected within 100 m of the AWAR, the Road Utilisation Work Suspension Protocol as per the TEMMP is implemented” and “During periods when herds of caribou (50 or more individuals) are detected within 100m of the AWAR, the southern gate is closed to traffic” are incorrect based on the recent revision to TEMMP Version 5, indicating a 300 m distance threshold trigger.Request: correct the threshold trigger in the Roads Management Plan. SDFN/NDFN Table 2, Comment 5: (App.H s.6.2.3) Even with low 2025 detections, Figure 6.2-4 shows caribou continue to regularly use the southeast Meliadine crossing. Before starting Discovery deposit development, AEM should not continue a 'business as usual' approach; caribou use at the 'Narrows' crossing has declined since the mine became operational and a similar reduction may occur here. Request: AEM should begin to develop an adaptive management plan for this key caribou crossing at the southeast end of Meliadine Lake to mitigate planned construction and new road/waterline infrastructure to ensure minimal impacts to caribou. Based on the baseline monitoring to date, it is recommended that AEM consider re-routing the Discovery Road further south so that it does not create a bottleneck barrier so close to the caribou crossing.
55 | Monitor wildlife mortality | Agnico Eagle GN KivIA | Terrestrial Environment Management and Monitoring Plan (TEMMP) (NIRB Doc ID 354044) | As per the TEMMP, wildlife mortalities are reported and thresholds are applied. The Inuit Impact Benefit Agreement (IIBA) between Agnico Eagle and the Kivalliq Inuit Association addresses compensation relative to wildlife mortality resulting from the Project. | 2025 Annual Report section 7.9 and related appendix (Appendix 25 2025 TEMMP Report) | [5 empty] | The KivIA has not heard about any caribou deaths and notes that the Annual Report (App. 25; S. 9.5) did not list any caribou deaths. | The TEMMP sets a 20 fox annual mortality threshold, which the GN maintains is notably different from earlier TEMMPs. Although the 2025 TEMMPR states this threshold was not exceeded, it does not report the number of fox deaths or clearly identify the definitive source for this information. GN #02: The current TEMMP sets a 20-fox annual mortality threshold, which the GN maintains is notably higher than earlier TEMMPs and the 2014 FEIS. The 2025 TEMMP Report (Table 16) states the threshold was not exceeded but Section 9.6 does not report how many foxes died in 2025 nor cross-reference where this is found. Appendix 26 (2025 Wildlife Observations) records mortalities including fox, but it is unclear whether it is the definitive source. Request: 1. Justify the increased mortality threshold for arctic fox. 2. Improve cross-referencing within annual reporting documents, including in this instance. | SDFN/NDFN Table 2, Comment 4: (B.1_0740666_Meliadine_ Caribou Blasting Memo-April 30, 2025 Figure 1.1 indicates surface and propane-cannon blasts occurred for several days just before the May 12 implementation of a Level 3 caribou migration protocol. Although collared caribou were 12–17 km away, small groups may have been nearer, and foggy weather (low winds) can propagate noise great distances. AEM could not detect caribou due to fog until informed by local hunters. Request: AEM should implement a precautionary action into the Caribou Protection Measures decision tree whereby surface and propane cannon blasting should not be conducted under Level 2, if the weather is foggy and caribou cannot be detected.
56 | Terrestrial environment monitoring annual reporting | Agnico Eagle |  | Terrestrial environment monitoring monitoring and mitigation measures are reported within the Annual Report. TAG activities are reported within the TAG Annual Report. | 2025 Annual Report Sections 7.9, 11.11 and related appendices (Appendix 25 2025 TEMMP Report, Appendix 37 2025 TAG Report) | [5 empty] | The KivIA undertakes monitoring on IOL and works with Agnico Eagle staff to implement TEMP monitoring and mitigation. The KivIA has reviewed the monitoring in the Annual Report and has comments and recommendations - see Effects Monitoring comments KivIA 02 KivIA 02: The KivIA does not agree that the preliminary threshold for sensory disturbance should be restricted to <10% deflection of caribou movements. The monitoring methods for the Monitoring Indicator ‘Sensory disturbance’ are based on Caribou satellite collar data, special studies and caribou behaviour monitoring. Each of those methods collects specific data which should be applied to measuring sensory disturbance. The Annual Report does not include an analysis of the 2025 collared caribou data to measure the rate of deflections. The special studies and behavior study are not applied to measure sensory disturbance. Without having a clear understanding of how to measure sensory disturbance it is not possible to describe effects on caribou or how effective their mitigation is. Request: The KivIA requests that Agnico Eagle develop clear thresholds to measure sensory disturbance.
57 | Examine trends in natural variability of each Valued Ecosystem Components (VECs), analyze wildlife responses to the Project, assess cumulative effects, and identify adaptive management actions | Agnico Eagle |  | The 2025 TEMMP Report and complementary studies included in Appendices include analysis of wildlife behaviour and adaptive management actions. | 2025 Annual Report Section 7.9.1 and 11.11, and related appendices (Appendix 25 2025 TEMMP Report, 2025 Caribou Behavior Report, 2025 Caribou Camera Report, Appendix 37 2025 TAG Report) | [5 empty] | The KivIA has reviewed the monitoring and mitigation and natural variability in the Annual Report and has comments and recommendations - see Effects Monitoring comments KivIA 03 KivIA 03: The Annual Report (App.25; S. 12.5) does not reach a conclusion about the annual shift in the extent of calving. The KivIA is concerned that Agnico Eagle has not analysed the shift for the extent of calving and related it to environmental trends such as earlier plant green up. Between 2017 and 2023, the annual core calving ground progressively shifted southeast but in 2014 and 2025, the core calving shifted to west of the RSA. The reporting of the extent of calving in 2025 is uninformative and should have included, for example, the trend since 2017 in the distance between annual centroids and their direction would be useful. Agnico Eagle acknowledges that calving is responsive to green-up but does not provide sufficient information to detect a trend in the timing of plant green up (App.25; Table 12) although acknowledging the importance of early green up for the timing of calving (App.29- 17; S. 3.1.4) Request: The KivIA requests that to measure trends in the natural variability, Agnico Eagle should analyse for a spatial trend in the core and extent of calving and whether the trend relates to a trend in the timing of plant green up. |  | SDFN/NDFN Table 2, Comment 2: (App 25, App G, Section 5.1,P.10, top paragraph, second last sentence)The statement that caribou may exhibit alert/running behaviours without a 'disturbance occurring' should be re-phrased to 'without a visual or auditory disturbance detected by the surveyor occurring.' Caribou detect disturbances with all senses; responses could be due to smell, taste, or touch not detectable by the observer. AEM should expand its assessment of how caribou respond to other sensory disturbances (ground vibration, vegetation palatability, fugitive emissions). Request: re-phrase the sentence on P.10 with the suggested wording. SDFN/NDFN Table 2, Comment 3: (App 25, App H, Table 5.1-1) Of 38 cameras deployed in 2025, six were stolen and four malfunctioned; deployment dates and effort (1,225 trap-nights) imply ~827 lost camera-days, and it is unclear which locations (AWAR/Mine/Discovery) lost data, calling the data's usefulness into question. Text/figure discrepancies exist on first-detection dates, and the 'no strong avoidance' summary overstates what the camera study (not designed to measure avoidance) can conclude. Request: AEM needs to indicate how many cameras were stolen or malfunctioning based on AWAR, Mine, and/or Discovery location deployment and how many camera-days of data were collected/lost by AWAR, Mine, and Discovery cameras. AEM should show an example calculation to explain how they arrived at their detection rates in 2025. Please clarify the discrepancies between the report text and figures in Section 6 “Results and Discussion.” SDFN/NDFN Table 2, Comment 8: (Section 7.9.1) The sentence states “Fewer than 30% of Qamanirjuaq caribou come within 5 km of the Project and 99% of caribou that came within 5 km of the AWAR or Mine for a specific year remained for less than 24 hours.” While it can be assumed this statement is referring to collared caribou, to someone reading this for the first time, it sounds like AEM is making a general statement about the entire Qamanirjuaq caribou herd, which would be misleading. Request: re-phrase by adding the word 'collared' before 'Qamanirjuaq' and after '99% of,' for clarity.
58 | Ensure all employees receive awareness training regarding the importance of avoiding known nests and nesting areas and avoiding large concentrations of foraging and moulting birds | Agnico Eagle | Terrestrial Environment Management and Monitoring Plan (TEMMP) (NIRB Doc ID 354044) | Bird awareness training (toolboxes) are provided to employees on a regular basis by the Environment Department. Training is provided to vessel captains and crews from the shipping companies. | 2025 Annual Report Section 7.9 and related appendices (Appendix 25 2025 TEMMP Report, Appendix 27 2025 MMSO Report)
59 | Establish clear zones of avoidance based on the species-specific nest setback distances outlined in the Terrestrial Environment Management and Monitoring Plan | Agnico Eagle | Terrestrial Environment Management and Monitoring Plan (TEMMP) (NIRB Doc ID 354044) | As per the TEMMP, nest surveys are carried out prior to construction activities and mitigation measures including setback distances are applied. | 2025 Annual Report Section 7.9 and related Appendix 25 2025 TEMMP Report
60 | Update the mitigation and monitoring strategies developed for Species at Risk as necessary | Agnico Eagle | • Terrestrial Environment Management and Monitoring Plan (TEMMP) (NIRB Doc ID 354044) • Shipping Management Plan (NIRB Doc IDs 354041, 354042, 354046) | Mitigation and monitoring strategies for Species at Risk are maintained in alignment with the TEMMP and Shipping Management Plan.
61 | Construction and clearing activities – deterrents and checks for nests before disturbance | Agnico Eagle | Terrestrial Environment Management and Monitoring Plan (TEMMP) (NIRB Doc ID 354044) | Prior to the 2025 breeding season, Agnico Eagle implemented nesting deterrents at multiple locations. Pre-clearing nest surveys were conducted, and mitgation measures implemented per TEMMP requirements. Nest data were included in the 2025 TEMMP Report. | 2025 Annual Report Section 7.9 and related Appendix 25 2025 TEMMP Report
62 | Establish setbacks from any nests found | Agnico Eagle | Terrestrial Environment Management and Monitoring Plan (TEMMP) (NIRB Doc ID 354044) | As per the TEMMP, nest surveys are carried out prior to construction activities and mitigation measures including setback distances are applied. | 2025 Annual Report Section 7.9 and related Appendix 25 2025 TEMMP Report
63 | Report bird mortalities to ECCC (Canadian Wildlife Services) | Agnico Eagle ECCC | Shipping Management Plan (NIRB Doc IDs 354041, 354042, 354046) | No incidents with seabird were reported for the 2025 shipping season. | 2025 Annual Report section 7.9.2 and related appendix (Appendix 27 2025 MMSO Report)
64 | Devlop a monitoring framework for monitoring marine birds and bird habitat in the event of a major marine fuel spill | Agnico Eagle | • Shipping Management Plan (NIRB Doc IDs 354041, 354042, 354046) • Marine Environment Management Plan (in appendix of the SMP) | The Shipping Management Plan and Marine Environment Management Plan (MEMP) outline monitoring and response measures for potential marine fuel spills.
65 | Maintain reduced speeds to sufficiently ensure that wakes are equal or less than the mean natural seasonal wave height | Agnico Eagle | Shipping Management Plan (NIRB Doc IDs 354041, 354042, 354046) | The Shipping Management Plan is shared with the shipping companies and implemented. Vessel crews receive training prior to each shipping season. | 2025 Annual Report section 7.9.2 and related appendix (Appendix 27 2025 MMSO Report)
66 | Check all vessels for suspected bird strikes | Agnico Eagle | Shipping Management Plan (NIRB Doc IDs 354041, 354042, 354046) | The MMSO program includes protocol for monitoring and reporting bird strikes. In 2025, no bird strikes were reported. | 2025 Annual Report section 7.9.2 and related appendix (Appendix 27 2025 MMSO Report)
67 | Updated Oil Pollution Prevention Plan | Agnico Eagle | • OPEP/OPPP (NIRB Doc ID 354032) • Shipping Management Plan (NIRB Doc IDs 354041, 354042, 354046) • Marine Environment Management Plan (in appendix of the SMP) | An updated OPEP/OPPP is maintained and implemented, along with the Shipping Management Plan and Marine Environment Management Plan.
68 | Consider potential cumulative effects of other projects and shipping activities on marine birds in the Hudson Strait | Agnico Eagle |  | The 2022 Shipping Cumulative Effects Technical Memo (appended to the 2022 Annual Report) and ongoing (yearly) MMSO data collection support the cumulative effects assessment of marine shipping on birds. | 2025 Annual Report Section 7.9.2 and related appendix (Appendix 27 2025 MMSO Report) 2022 Shipping Cumulative Effects Technical Memo in Appendix 29 of the 2022 Annual Report (NIRB Doc ID 343924)
69 | Flight altitude requirements – horizontal and vertical distances | Agnico Eagle | Terrestrial Environment Management and Monitoring Plan (TEMMP) (NIRB Doc ID 354044) | The flight altitude requirements are included in the TEMMP.
70 | Flight altitude requirements – minimum cruising altitude guidelines and flight record log | Agnico Eagle | Terrestrial Environment Management and Monitoring Plan (TEMMP) (NIRB Doc ID 354044) | The flight altitude requirements are included in the TEMMP. | [5 empty] | TC-04: TC 70 deals with flight altitudes to and from the Meliadine Mine aerodrome. Transport Canada received no complaints related to this aerodrome in 2025 and conducted no site inspections or enforcement activities related to the aerodrome in 2025.
71 | Develop detailed and robust mitigation and monitoring plans for migratory birds | Agnico Eagle KivIA HTOs Communities | Terrestrial Environment Management and Monitoring Plan (TEMMP) (NIRB Doc ID 354044) | Monitoring and mitigation are part of the TEMMP and results are included in the TEMMP Report. | 2025 Annual Report Section 7.9 and related Appendix 25 2025 TEMMP Report
72 | Monitoring with key indicators in the Environmental Protection Plan and Terrestrial Environment Mitigation and Monitoring Plan (TEMMP) | Agnico Eagle | • Terrestrial Environment Management and Monitoring Plan (TEMMP) (NIRB Doc ID 354044) • Shipping Management Plan (NIRB Doc IDs 354041, 354042, 354046) | Monitoring and management updates are included in the TEMMP and detailed in the TEMMP report. | 2025 Annual Report Section 7.9 and related Appendix 25 2025 TEMMP Report
73 | Monitor and report on terrestrial habitat losses | Agnico Eagle |  | See T&C35. Habitat loss was last assessed in 2024 (Appendix 26 2024 TEMMP Report). The next assessment will be in 2027. | 2025 Annual Report Section 7.9 and related Appendix 25 2025 TEMMP Report
74 | Include measures to prevent use of water attenuation ponds by waterfowl and waterbirds into the Terrestrial Environment Mitigation and Monitoring Plan (TEMMP) | Agnico Eagle | • Terrestrial Environment Management and Monitoring Plan (TEMMP) (NIRB Doc ID 354044) • Shipping Management Plan (NIRB Doc IDs 354041, 354042, 354046) | Mitigation and monitoring are included in the TEMMP and Shipping Management Plan. Results are presented in the Annual Report (TEMMP Report and MMSO Report). | 2025 Annual Report Sections 7.9.1, 7.9.2 and related appendices (Appendix 25 2025 TEMMP Report, Appendix 27 2025 MMSO Report)
75 | Implement mitigation measures and monitoring programs to limit the attraction of predators and scavengers to Project facilities | Agnico Eagle | • Terrestrial Environment Management and Monitoring Plan (TEMMP) (NIRB Doc ID 354044) • Landfill and Waste Management Plan (NIRB Doc ID 354034) | Mitigation measures including waste management practices are implemented to reduce the attraction of predators to the Mine facilities. | 2025 Annual Report Section 7.9 and related Appendix 25 2025 TEMMP Report
76 | Update all Relevant Plans for the Marine Environment | Agnico Eagle | • Spill Contingency Plan (NIRB Doc ID 354043) • OPEP/OPPP (NIRB Doc ID 354032) • Shipping Management Plan (NIRB Doc IDs 354041, 354042, 354046) • Marine Environment Management Plan (in appendix of the SMP) | Relevant plans were updated to address the marine environmental protection. Monitoring results and mitigation measures are reported in the Annual Report. | 2025 Annual Report section 7.9.2 and related appendix (Appendix 27 2025 MMSO Report) |  | The Shipping Management Plan indicates that shipping vessels must follow a setback distance of 2 km from Marble Island. The 2025 Annual Report indicates that “Groupe Desgagnés and/or Woodward vessel tracks crossed through the 2 km setback polygon at Marble Island on three occasions,” due to bad weather. Marine mammal surveys are conducted for 1.5-2 hours and typically only once per day. DFO recommends that if ships need to enter these sensitive marine areas, marine mammal monitoring will be conducted for the entirety of the transit through the area. Please see DFO related standards for marine mammal observers: https://waves-vagues.dfo-mpo.gc.ca/library-bibliotheque/41330730.pdf The introduction of Aquatic Invasive Species (AIS) to shipping ports of the arctic remains a serious concern for DFO. Although AEM contracts independent companies for shipping, which are themselves responsible for meeting regulations and compliance, as it stands there is no monitoring program or response plan for aquatic invasive species associated with the shipping related to the AEM mining activities. There is a risk of introducing aquatic invasive species through hull contamination and ballast water exchange from ships coming from other regions. The Shipping Management Plan requires the shipping companies contracted to supply the Meliadine Mine through the annual sea-lift operations to comply with the Ballast Water Regulations, which reduces the risk of invasive species being introduced as a result of shipping activities, but does not eliminate this risk. Monitoring for the presence of aquatic invasive species at ports would be required for AIS detection, and the development of a AIS Monitoring and Management Plan would be a necessary first step towards developing an appropriate AIS mitigation strategy. Underwater noise from shipping vessels has the potential to elicit disturbance effects on marine mammals by reducing their ability to travel, communicate, and find food. This issue remains a concern for DFO. During the 2025 shipping season, 15 vessel trips served the Meliadine project. It remains unknown what noise levels and characteristics are produced by those shipping vessels and the potential impact on marine mammals. The FEIS predicted the residual environmental effect of a change in marine mammal behaviour as a result of Project vessel noise was considered to be low in magnitude, however the likelihood of behavioural disturbance from Project-related vessel noise was considered likely. There is currently no monitoring of noise levels to help understand and mitigate these effects.
77 | Maintain the necessary equipment and trained personnel to respond to all sizes of potential spills associated with the Project | Agnico Eagle | • Spill Contingency Plan (NIRB Doc ID 354043) • OPEP/OPPP (NIRB Doc ID 354032) | Required equipment and trained personnel are maintained in accordance with relevant Plans for spill response. Mock spill exercices are carried out and details are included in the Annual Report. | 2024 Annual Report Section 6 and 12.4.7, and related appendix (Appendix 17 2025 Mock Spill Report)
78 | Conduct fuel spill dispersion modelling | Agnico Eagle | Shipping Management Plan (NIRB Doc IDs 354041, 354042, 354046) | See T&C77. | 2024 Annual Report Section 6 and 12.4.7, and related appendix (Appendix 17 2025 Mock Spill Report)
79 | Updated Baseline for Shipping Management Plan | Agnico Eagle | Shipping Management Plan (NIRB Doc IDs 354041, 354042, 354046) | The Shipping Management Plan and Marine Environment Management Plan (MEMP) were updated with baseline information prior to project-related shipping. Findings from the MMSO program continue to guide management practices. | 2025 Annual Report section 7.9.2 and related appendix (Appendix 27 2025 MMSO Report)
80 | Assess baseline information for Melvin Bay | Agnico Eagle | Shipping Management Plan (NIRB Doc IDs 354041, 354042, 354046) | The marine baseline data for Melvin Bay and the fuel transshipment anchorage is based on the 2016 Revised Marine Environmental Baseline Report, included in the 2017 MEMP.
81 | Ensure relevant plans incorporate mitigation and monitoring programming for marine wildlife | Agnico Eagle | • Shipping Management Plan (NIRB Doc IDs 354041, 354042, 354046) • Marine Environment Management Plan (in appendix of the SMP) | The TEMMP and Shipping Management Plan include mitigation measures to reduce impacts on marine mammals. IQ was integrated thorugh meetings, site visits, cultural activities. | 2025 Annual Report Sections 7.9.1, 7.9.2 and related appendices (Appendix 25 2025 TEMMP Report, Appendix 27 2025 MMSO Report)
82 | Require all contracted shipping companies to provide full-time marine wildlife monitoring using trained observers and established data collection and recording protocols | Agnico Eagle | Shipping Management Plan (NIRB Doc IDs 354041, 354042, 354046) | The MMSO program continued in 2025 with trained observers and standardized protocols, as per the Shipping Management Plan. | 2025 Annual Report section 7.9.2 and related appendix (Appendix 27 2025 MMSO Report) |  | The Meadowbank and Meliadine Mines Marine Mammal and Seabird Report, 2025, indicates that Marine Mammal Monitoring survey efforts in 2025 were conducted at an effort of 1.5-2 hours per survey, but not indicating the number of surveys being conducted daily, which was previously 1-3 surveys per day. One survey daily is not sufficient for effective marine mammal monitoring. DFO would like to point out that the wording, "full-time marine wildlife monitoring", contained within this term and condition, suggests that monitoring will occur for a significant amount of time while the vessel is under voyage. DFO recommends that more marine mammal monitoring be undertaken, especially while ships are passing through restricted areas such as north of Coats Island and within 2 km of Marble Island.
83 | Minimize marine mammal interactions (e.g., give wildlife the right way) | Agnico Eagle | Shipping Management Plan (NIRB Doc IDs 354041, 354042, 354046) | Project vessels operate in accordance with the Shipping Management Plan, with mitigation measures implemented to reduce potential interactions with marine mammals and seabirds. | 2025 Annual Report section 7.9.2 and related appendix (Appendix 27 2025 MMSO Report)
84 | Plan shipping routes to avoid terrestrial walrus haulouts | Agnico Eagle | Shipping Management Plan (NIRB Doc IDs 354041, 354042, 354046) | Shipping routes were planned in accordance with the Shipping Management Plan to avoid terrestrial walrus haulouts and sensitive marine habitats. | 2025 Annual Report section 7.9.2 and related appendix (Appendix 27 2025 MMSO Report)
85 | Monitor disturbance to walruses | Agnico Eagle |  | Monitoring is conducted as part as the MMSO program. | 2025 Annual Report section 7.9.2 and related appendix (Appendix 27 2025 MMSO Report)
86 | Consider cumulative effects on marine wildlife in the region | Agnico Eagle |  | Cumulative effects monitoring is supported through coordinated MMSO reporting with the Meadowbank project. | 2025 Annual Report section 7.9.2 and related appendix (Appendix 27 2025 MMSO Report) 2022 Shipping Cumulative Effects Technical Memo in Appendix 29 of the 2022 Annual Report
87 | Participate in the work of the Kivalliq Socio-Economic Monitoring Committee (KSEMC) | Agnico Eagle |  | The KvSEMC meets annually to review mining impacts in the Kivalliq region. Agnico Eagle participates in these meetings. | 2025 Annual Report Section 12
88 | Establish a socio-economic working group for the Project | Agnico Eagle GN CIRNAC Communities |  | Agnico Eagle continues to work with socio-economic stakeholders through the Socio-Economic Monitoring Working Group (SEMWG), which includes GN, CIRNAC, and KivIA. Also see the SEMWG Terms of Reference. | 2025 Annual Report Section 12.1 and related Appendix (Appendix 38 2025 Socio-Economic Monitoring Report) | CIRNAC - The department’s Nunavut Regional Office is a member of the Agnico Eagle Kivalliq Projects Socio‑Economic Monitoring Working Group. Through this working group, the department contributes to the collaborative analysis and interpretation of data for reporting purposes and assesses the effectiveness of project‑related activities. The department also provides updates on actions under the Nunavut General Monitoring Plan. As the plan continues to be developed, relevant indicators and socio‑economic monitoring data will be made available. | [5 empty] | The GN has no comments regarding this TC at this time.
89 | Develop the Meliadine Socio-economic Monitoring Program | Agnico Eagle KivIA GN CIRNAC Communities |  | The Agnico Eagle Kivalliq Projects Socio-Economic Monitoring Program is in place and reported annually. | 2025 Annual Report Section 12.1 and related Appendix (Appendix 38 2025 Socio-Economic Monitoring Report) | CIRNAC - Through its participation in the Agnico Eagle Kivalliq Projects Socio‑Economic Monitoring Working Group, the department contributes to the review and implementation of the Kivalliq Socio‑Economic Monitoring Program, which is authored by Agnico Eagle. The working group provides a forum to discuss its associated monitoring plan and review socio‑economic data collected through the program. |  |  |  |  | KivIA 14: Inuit workforce participation remains near ~10% overall while turnover is substantially above industry benchmarks, with Inuit underrepresented in skilled trades, technical, supervisory, and management roles, indicating a 'pipeline bottleneck' in upward mobility. There is insufficient discussion of contractors' activities to hire, train, retain, and advance Inuit. Request: Review and improvement of current employee upskilling, and employee readiness training programs to support a better understanding of the future potential of mine sites. Provide solutions to improving Contractors’ activities and efforts to improve Inuit employment at the sites. Confirm the number of Inuit employees who have developed a Career development plan with their supervisor. Confirm the number of supervisors who have been trained to complete a career development plan with their Inuit employees. Confirm the participants in the RISE program and their specific turnover rate. | The GN has no comments regarding this TC at this time.
90 | Analyze risk of temporary mine closure | Agnico Eagle |  | Agnico Eagle submitted an Analysis of the Risk of Temporary Mine Closure in February 2019 (NIRB Doc ID 324985). The findings and risk assessment outlined in the 'Risk of Temporary Mine Closure' report remain applicable to the ongoing operations at Meliadine. The existing content continues to accurately reflect the potential risks and mitigation strategies associated with temporary mine closure scenarios. Should any significant changes in operational conditions or external factors arise that would necessitate a reassessment, Agnico Eagle will revaluate the need for an updated report accordingly.
91 | Updated Socio-Economic Management Plan after risk plan submitted | Agnico Eagle |  | As per the SEMWG Terms of Reference, the SEMP will be updated 2 years prior to closure to include data collection, analysis, and mitigation measures for potential socio-economic impacts in the closure and post-closure phases. | 2025 Annual Report Section 12.1 and related Appendix (Appendix 38 2025 Socio-Economic Monitoring Report)
92 | Submit a detailed staff schedule | Agnico Eagle |  | The employment schedule was submitted in May 2019. (NIRB Doc ID 325135)
93 | Register all trades occupations, journeypersons and apprentices | Agnico Eagle |  | The annual SEMP Report includes information on registered apprentices and journeypersons employed at the Mine. | 2025 Annual Report section 12 and related Appendices
94 | Update labour force analysis | Agnico Eagle |  | In 2023, Agnico Eagle and KivIA’s Employment and Culture Committee signed an MOU to update the Kivalliq Labour Market Analysis (KLMA) on a three-year cycle. The last KLMA was completed in 2024 and reported in the 2024 Annual Report. | 2024 Annual Report section 12.5.2 and related Apppendix 41 (2024 Kivalliq Labour Market Analysis Executive Summary) (NIRB Doc ID 354028)
95 | Work with traning organizations to provide opportunities for residents and employees to gain meaningful and transferable skills and certifications | Agnico Eagle KivIA GN Municipal Training Org |  | Agnico Eagle tracks training through its Training Management System (TMS). Agnico Eagle considers that most of the trainings provided would be transferable to other employment opportunities. Records are available to employees. | 2025 Annual Report section 12.3, 12.4 and related Appendix (Appendix 39 2025 Training) | [5 empty] | KivIA 13: Reporting emphasizes program delivery and activity metrics rather than measurable long-term outcomes (educational attainment, workforce retention, career advancement, Inuit representation in skilled/leadership positions). The Underground Trainee Program reported only 5 completions of 11 participants (~45% non-completion). Inuit representation remains concentrated in unskilled roles, and there is reliance on structural barriers as explanations rather than a systemic review of AEM's effectiveness; contractors represent ~50% of the workforce. Request: Review and improvement of current employee upskilling, and employee readiness training programs to focus on desired outcomes (i.e., improved Inuit employment at higher skill levels) and to improve our mutual understanding of the future potential employment benefits of the mine sites. | The GN has no comments regarding this TC at this time.
96 | Develop a listing of formal certificates and licences that may be acquired via on-site training or training during Project employment | Agnico Eagle |  | Agnico Eagle tracks training through its Training Management System (TMS). Agnico Eagle considers that most of the trainings provided would be transferable to other employment opportunities. Records are available to employees. | 2025 Annual Report section 12.3, 12.4 and related Appendix (Appendix 39 2025 Training)
97 | Monitor potential impacts of closure on education and training | Agnico Eagle |  | See Analysis of the Risk of Temporary Mine Closure (NIRB Doc ID 324985).
98 | Work with the Kivalliq Socio-Economic Monitoring Committee (KSEMC) and monitor education utilization rates | Agnico Eagle |  | Education trends are reviewed with KvSEMC and SEMWG to monitor potential project impacts. | 2025 Annual Report Section 12.1 and related Appendix (Appendix 38 2025 Socio-Economic Monitoring Report)
99 | Work with the Kivalliq Socio-Economic Monitoring Committee (KSEMC) and monitor demographic changes | Agnico Eagle | Agnico Eagle Kivalliq Projects Socio-Economic Monitoring Program (NIRB Doc ID 354024) | Agnico Eagle monitors employee residence data and works with KvSEMC to assess demographic trends. | 2025 Annual Report Section 12 and related Appendix 38 2024 Socio-Economic Monitoring Program Report
100 | Work with the Kivalliq Socio-Economic Monitoring Committee (KSEMC) and offer a voluntary survey to Nunavummiut employees | Agnico Eagle GN | Agnico Eagle Kivalliq Projects Socio-Economic Monitoring Program (NIRB Doc ID 354024) | An annual Inuit and Nunavummiut Employment Survey, Tukisigiaqniq, is completed. | 2025 Annual Report Section 12 and related Appendix 38 2024 Socio-Economic Monitoring Program Report
101 | Monitor employee origin to compare predictions of labour availability and employment opportunities with actual levels of employment | Agnico Eagle | Agnico Eagle Kivalliq Projects Socio-Economic Monitoring Program (NIRB Doc ID 354024) | The required information is reported annually in the Annual Report. Details are included in the SEMP Report. | 2025 Annual Report Section 12 and related Appendix 38 2024 Socio-Economic Monitoring Program Report
102 | Provide detailed design details of Meliadine Lake Community Boat Launch showing consideration for public and worker safety | Agnico Eagle |  | Not Yet Active / Not Yet Applicable
103 | Have community level input into monitoring plans, programs, and mitigative measures | Agnico Eagle KivIA HTOs |  | Agnico Eagle has continued to engage with Kivalliq communities through meetings, events, and workshops, including activities with the Kivalliq Elders Advisory Committee and the Terrestrial Advisory Group. | 2025 Annual Report section 11 and related Appendices (Appendix 34 2025 Community Engagement Table, Appendix 36 KEAC Summary Report, Appendix 37 2025 TAG Annual Report)
104 | Consult with outfitting and guiding businesses regarding use of the area | Agnico Eagle |  | Agnico Eagle engages with local outfitters and community members through the HHS. | 2025 Annual Report section 7.9.1, 11.7 and related Appendices (Appendix 25 2025 TEMMP Report, which includes the 2025 Hunter Harvest Study Report)
105 | Consider incorporating information obtained from local outfitting and guiding businesses into its Hunter Harvest Survey where possible | Agnico Eagle |  | The 2025 Hunter Harvest Study included 69 participants, including outfitters and guides from Rankin Inlet, contributing to the havest data. | 2025 Annual Report section 7.9.1, 11.7 and related Appendices (Appendix 25 2025 TEMMP Report, which includes the 2025 Hunter Harvest Study Report)
106 | Inspection reporting for spring freshet and ice-free period at bridge crossings | Agnico Eagle GN |  | Agnico Eagle conducts regular inspections at key locations during pre-freshet, freshet and open water season. Mitigation measures are implemented as needed as per the Sediment and Erosion Management Plan. | 2025 Annual Report Section 7.5
107 | Address ice buildup on bridge crossings | Agnico Eagle GN | Roads Management Plan (NIRB Doc ID 354037) | Measures are outlined in the Roads Management Plan to monitor ice buildup at the lower Meliadine River Bridge.
108 | Provide access to counseling and treatment programs | Agnico Eagle |  | Agnico Eagle continues to support employee wellness through mental health services, cultural programming, and family-focused initiatives. | 2025 Annual Report section 12.2.3, and Appendix 38 2025 Socio-Economic Monitoring Program Report
109 | Work with the Kivalliq Socio-Economic Monitoring Committee (KSEMC) to monitor potential indirect effects of the Project on health and well being. | Agnico Eagle |  | Agnico Eagle continues to support wellness through mental health programs and community partnerships, including the Inunnguiniq initiative. | 2025 Annual Report section 12.1, and Appendix 38 2025 Socio-Economic Monitoring Program Report
110 | Encourage the on-site cohesion and wellbeing of employees through cultural awareness and wellness programs | Agnico Eagle |  | Agnico Eagle continues to refine its Cultural Awareness training to foster a deeper understanding of Inuit culture, values, and perspectives in the workplace. Details on the Cultural Awareness training and participation are included in the Annual Report. | 2025 Annual Report section 12.1, 12.4.2 and related Appendix 38 2025 Socio-Economic Monitoring Program Report | CIRNAC #6-TC 110 requires reporting, for each wellness/cultural program, the language of instruction, uptake rates, completion rates, and any content issues. Section 12.4.2 of the 2025 Annual Report and the 2025 Socio-Economic Monitoring Program Report describe the in-class Cross-Cultural Training Program, but do not fully address all of the required reporting elements. In particular, the report does not specify the language(s) of instruction, nor does it provide disaggregated participation data by Inuit and non‑Inuit employees. Request: future Annual Report submissions clearly demonstrate how Agnico Eagle is addressing the information requirements outlined in Condition 110 of Project Certificate No. 006, particularly those related to the implementation of its cultural awareness and wellness initiatives.
111 | Provide detailed descriptions of all employee programs and training | Agnico Eagle |  | Information on employees programs and trainings is included in the Annual Report. | 2025 Annual Report section 12.3 and 12.4 and related Appendix 38 2025 Socio-Economic Monitoring Program Report and Appendix 39 2025 Training
112 | Investigate measures and programs designed to assist Project employees with pursuing home ownership | Agnico Eagle |  | Agnico Eagle has engaged in collaborative discussions with the GN and the Nunavut Housing Corporation to explore potential measures that support home ownership and access to affordable housing for project employees in the Kivalliq region. | 2025 Annual Report section 12.5.1, and Appendix 38 2025 Socio-Economic Monitoring Program Report
113 | Design and implement an annual employee housing and migration survey | Agnico Eagle GN |  | An annual Inuit and Nunavummiut Employment Survey, Tukisigiaqniq, is completed. Housing and migration data is gathered. | 2025 Annual Report Section 12 and related Appendix 38 2025 Socio-Economic Monitoring Program Report | [6 empty] | The GN has no comments regarding this TC at this time.
114 | Collaborate with GN prior to the development and inception of programs relating to financial literacy | Agnico Eagle GN |  | Agnico Eagle collaborated with the GN and Nunavut Housing Corporation to explore housing-related supports and incorporated financial literacy training into pre-employment programs. | 2025 Annual Report Section 12.5 and related Appendix 38 2025 Socio-Economic Monitoring Program Report | [6 empty] | The GN has no comments regarding this TC at this time.
115 | Work with GN and monitor impacts of the Project on the health services | Agnico Eagle GN |  | Agnico Eagle maintains on-site health services and referred 82 employees to community clinics in 2025, mostly for non-work-related issues. | 2025 Annual Report, Appendix 38 2025 Socio-Economic Monitoring Program Report | [6 empty] | The GN has no comments regarding this TC at this time.
116 | Update the air quality monitoring aspect of its environmental and health risk monitoring program | Agnico Eagle GN | Air Quality Monitoring Plan (NIRB Doc ID 354009) | Agnico Eagle conducted year-round air quality monitoring in 2025, including dustfall, particulate matter, and metals analysis. Results were generally below regulatory thresholds, with occasional exceedances attributed to localized events. | 2025 Annual Report section 7.8 and related Appendix 24 2025 Air Quality Monitoring Report | [6 empty] | The GN has no comments regarding this TC at this time.
117 | Operate Phase 2 of the AWAR and the Bypass Road in accordance with relevant legislation and regulations | Agnico Eagle KivIA Hamlets Communities |  | Not Yet Applicable (Phase 2 of the AWAR has not been yet constructed)
118 | Develop a decision tree outlining mitigation and monitoring steps to be implemented when caribou in specified group sizes are observed within specified distances of the Project's AWAR and waterlines | Agnico Eagle | Terrestrial Environment Management and Monitoring Plan (TEMMP) (NIRB Doc ID 354044) | Caribou monitoring and mitigations measures are implemented as per the TEMMP. The TEMMP was updated with TAG input. | 2025 Annual Report section 7.9.1 and related Appendix 25 2025 TEMMP report
119 | Establish deterrents along the AWAR where caribou attraction is observed | Agnico Eagle | • Terrestrial Environment Management and Monitoring Plan (TEMMP) (NIRB Doc ID 354044) • Spill Contingency Plan (NIRB Doc ID 354043) | The TEMMP and Spill Contingency Plan are implemented. Spill prevention principles related to waterlines and caribou protection are outlined in the plans. | 2025 Annual Report section 7.9.1 and related Appendix 25 2025 TEMMP report
120 | Contract only TC certified shippers and ensure all relevant plans are followed | Agnico Eagle | • OPEP/OPPP (NIRB Doc ID 354032) • Shipping Management Plan (NIRB Doc IDs 354041, 354042, 354046) | Agnico Eagle contracts Transport Canada-certified shipping companies. The Shipping Management Plan and OPEP/OPPP are implemented. | 2025 Annual Report section 10.4 and related Appendix (Appendix 27 2025 MMSO Report) |  |  |  |  | TC-05: No TDG monitoring was carried out at the Meliadine Mine site by Transport Canada's TDG group in 2025. No TDG complaints/concerns were received and no enforcement actions were undertaken in 2025. TC-06: Appendix 13 provides a list/summary of hazardous (dangerous) goods shipped from site. It would assist future reviews if copies of the dangerous goods shipping documents were included with the annual report rather than only a summary. Request: that NIRB bring this to AEM's attention.
121 | Monitor ingress/egress of Project related ships at Rankin Inlet and report and accidents or spills | Agnico Eagle | • Shipping Management Plan (NIRB Doc IDs 354041, 354042, 354046) • Spill Contingency Plan (NIRB Doc ID 354043) | Vessel ingress/egress at Rankin Inlet is monitored throughout the shipping season and spills are reported as per the Spill Contingency Plan. | 2025 Annual Report section 7.9.2, 10.4 and related Appendix (Appendix 27 2025 MMSO Report)
122 | Ensure that best practices are used at all times during ship to shore and other marine-based fuel transfer events | Agnico Eagle | • OPEP/OPPP (NIRB Doc ID 354032) • Shipping Management Plan (NIRB Doc IDs 354041, 354042, 354046) | Post Oil Transfer Reports were submitted to Transport Canada following the 2025 fuel transfers. | [5 empty] | TC-02: Transport Canada recommends the Proponent make vessel operators serving the Project aware of the 2026 Annual Notice to Mariners, in particular section A2 (Marine Mammal Guidelines and Marine Protected Areas), section 7A (Voyage Planning for Vessels Intending to Navigate in Canada's Northern Waters), and section 7C (Vessels Intending to Navigate in the Kitikmeot Region). Request: that this information be brought to AEM's attention.
123 | Ensure that the necessary spill response equipment and training is available | Agnico Eagle | • Shipping Management Plan (NIRB Doc IDs 354041, 354042, 354046) • Spill Contingency Plan (NIRB Doc ID 354043) • OPEP/OPPP (NIRB Doc ID 354032) | Agnico Eagle maintains trained personnel and equipment for spill response. Details are included in the Spill Contingency Plan, OPEP/OPPP and Shipping Management Plan. | 2025 Annual Report section 6, 12.4.1 and related appendix (Appendix 17 2025 Mock Spill Scenario Report)
124 | Updated Spill Contingency Plan specific to a major spill event (including releases from the waterlines) occurring on the Bypass Road | Agnico Eagle | Spill Contingency Plan (NIRB Doc ID 354043) | The updated Spill Contingency Plan includes preparedness for major spills near Nipissar Lake and the Bypass Road. |  | CIRNAC #5-Discharge of up to 20,000 m³/day of saline water to the marine environment is one of the most significant variances to the FEIS water-management plans and predictions. Inability to comply with ECCC's Acartia tonsa acute toxicity testing requirements has been a critical constraint since 2022, yet the 2025 Annual Report contains no discussion of the status of AEM's efforts to meet that requirement, creating significant uncertainty about plans/schedules for initiating marine discharge. Request: Given the importance of saline water discharge to the marine environment, CIRNAC requests updated information regarding the status of Acartia tonsa toxicity management, including contingency measures if discharge toxicity objectives cannot be consistently achieved. |  |  |  |  | KivIA 08: KivIA requests using the summary-table format from the Non-Reportable Spills to summarize the Reportable Spills, allowing better tracking and easier identification of patterns/re-occurring issues to support future training and equipment maintenance. Request: summary table from the Non-Reportable Spills be used to summarize the Reportable Spills in the Annual Report for 2026.
125 | Ensure rules for use of the road are clearly communicated in the interest of providing for the health and safety of all users of the AWAR | Agnico Eagle | Roads Management Plan (NIRB Doc ID 354037) | The Roads Management Plan is implemented, including signage, gatehouse monitoring, and traffic data collection along the AWAR. Rules of the road are shared through community meetings and digital communication efforts. | 2025 Annual Report, sections 10.3, 11.9, 11.10
126 | Ensure clear and consistent communication of safety requirements and road use limitations to inform members of the public | Agnico Eagle | Roads Management Plan (NIRB Doc ID 354037) | The rules of the road are included in the Roads Management Plan and shared through community meetings and digital communication efforts. | 2025 Annual Report, sections 10.3, 11.9, 11.10
127 | Ensure adaptive management measures are available to address impacts to marine mammals | Agnico Eagle KivIA HTOs | Shipping Management Plan (NIRB Doc IDs 354041, 354042, 354046) | Findings from the MMSO program continue to guide management practices. | 2025 Annual Report section 11.9 and 11.10
128 | Provide detailed design for the waterlines system including location of pipeline, submerged collars and design of the diffuser | Agnico Eagle DFO ECCC CIRNAC |  | The detailed design was submitted to the NIRB on April 30, 2025. |  | CIRNAC was unable to locate the detailed design submission on the public registry. CIRNAC requests that AEM provide the public registry link (or document ID) for the detailed design submission and confirm it includes, at minimum, (i) pipeline location in relation to the saline effluent storage tank at Itivia, (ii) submerged collar locations, and (iii) diffuser design, along with the submission date and any subsequent revisions. | The detailed design was submitted to the NIRB on April 30, 2025. No updates to this information were included as part of the 2025 Annual Report. DFO has issued the following Letters of Advice for related work. For the Water Line and Road Widening: 19-HCAA-00552, 20-HCAA-02718, 22-HCAA-00513, 23-HCAA-00223, 24-HCAA-00619, and 25-HC-01837. For the Diffuser: 22-HCAA-00513.
129 | Conduct and submit a hazard and operability assessment of the pipeline and marine outfall system | Agnico Eagle CIRNAC |  | Not Yet Active/Not Yet Applicable |  | CIRNAC has no comments at this time
130 | Assess the environmental impact of the Project on the seabed and marine environment if the effluent discharge pipeline is abandoned in place or removed | Agnico Eagle CIRNAC ECCC TC DFO |  | Documentation provided to NIRB in June 2024 (NIRB Doc ID. 350702) |  | CIRNAC requests that AEM clarify whether the decommissioning and reclamation commitments for the waterline infrastructure at Itivia Harbour include onshore components, and where these commitments are reflected in closure planning and security assumptions. | Documentation provided to NIRB in June 2024. No updates to this information were included as part of the 2025 Annual Report. DFO has no comments. |  |  | TC confirms this statement is accurate.
131 | Engage the HTO to confirm annual open‑water season dates for marine effluent discharge and work with the HTO and community to develop monitoring for effluent temperature, Melvin Bay ice thickness, and related community communication and safety protocols | Agnico Eagle |  | Not applicable for 2025 as there was no marine effluent discharge.
132 | Establishment of a Terrestrial Advisory Group | Agnico Eagle NTI KivIA KWB GN HTOs SDFN NDFN |  | The TAG Term of References (TORs) were finalized early 2023. The TAG held 1 meeting in 2025. | 2025 Annual Report Section 11.11 and related Appendix 37 2025 TAG Report | [6 empty] | On April 10, 2026, the Proponent sent a letter notifying members that the Meliadine TAG was being dissolved and replaced by two new groups, the Qamanirjuaq Herd Observation Committee and the Kangiqliniq Studies Committee and this change was intended to help satisfy TC 132. The GN cannot support the changes proposed by the Proponent to the Meliadine Terrestrial Advisory Group (TAG) at this time but remains open to continued discussion through the TAG regarding how to improve efficiency and may consider structural or membership changes as part of the collaborative review of the TAG TOR under TC 132 with existing TAG members. GN #03: The GN is awaiting additional information on the rationale and is currently unable to comment on whether TC 132 is being effectively implemented. Request: N/A | A meeting of the TAG to address matters relating to terrestrial wildlife and wildlife habitat in accordance with the objective and mandate of the TAG and the requirements of T&C 132 has not been held since March 2025 and no meetings to discuss these issues has been scheduled for 2026. SDFN/NDFN request a TAG meeting be scheduled in 2026 to address matters relating to terrestrial wildlife and wildlife habitat in accordance with the objective and mandate of the TAG set out in T&C 132. SDFN/NDFN Table 2, Comment 6: The Annual Report states a TAG meeting took place in November to review environmental monitoring updates; however, that meeting was cancelled and no environmental updates occurred. Request: re-phrase the sentence to reflect that the TAG meeting did not occur. DFN/NDFN Table 2, Comment 7: A meeting was proposed for April 28–29, 2026, but on April 9, 2026 AEM purported the April 28 meeting was now a meeting of a new committee without prior TAG discussion/approval; SDFN/NDFN rejected this on April 21, 2026. The April 2026 meeting focused almost entirely on the TAG Terms of Reference. It has been over a year since the TAG met on terrestrial wildlife/habitat matters. Request: schedule a TAG meeting in 2026 to address terrestrial wildlife and wildlife habitat in accordance with the objective and mandate of the TAG set out in T&C 132.
133 | Update the Ocean Discharge Monitoring Plan to ensure additional monitoring verifies that waterline discharges cause no acute or chronic marine impacts | Agnico Eagle |  | Not Yet Active/Not Yet Applicable |  | CIRNAC #5-Discharge of up to 20,000 m³/day of saline water to the marine environment is one of the most significant variances to the FEIS water-management plans and predictions. Inability to comply with ECCC's Acartia tonsa acute toxicity testing requirements has been a critical constraint since 2022, yet the 2025 Annual Report contains no discussion of the status of AEM's efforts to meet that requirement, creating significant uncertainty about plans/schedules for initiating marine discharge. Request: Given the importance of saline water discharge to the marine environment, CIRNAC requests updated information regarding the status of Acartia tonsa toxicity management, including contingency measures if discharge toxicity objectives cannot be consistently achieved.
134 | Submit a summary of the waterlines’ construction, operation, maintenance, monitoring, and leak detection system | Agnico Eagle |  | Not Yet Active/Not Yet Applicable |  | CIRNAC #1-The waterline commissioning schedule has shifted across annual reports; Planned activities for 2026 now include minor construction, hydrotesting, and commissioning. There are inconsistencies among report sections on when waterline/WES02 discharge begins. Request: (1) Provide an assessment of risks associated with delayed commissioning of the saline discharge waterline, including implications for TIRI02/WES02 storage capacity, saline water quality evolution, and long-term dependence on interim onsite storage and treatment systems. (2) Clarify the status of the waterline and provide additional details on: a) Planned 2026 and 2027 construction and commissioning activities, b) Schedules for the start of saline water and contact water discharge at Itivia, and c) Expected operational practices (daily, monthly, annual discharge) upon start of discharge at Itivia.
Commitments, Project Certificate No. 006, Amendment 02
Commitment no. | Commitment Summary | Responsible Party / Authorities | Associated Plan(s) | Proponent Submission or Summary | Reference | CIRNAC | Additional Comments | ECCC | HC | TC | KivIA | GN | SDFN NDFN
1 | NIRB to appoint Monitoring Officer(s). | NIRB |  | N/A (NIRB)
2 | NIRB to report annually on the monitoring program (in English and Inuktitut). | NIRB |  | N/A (NIRB)
3 | NIRB to conduct periodic community meetings and updates regarding its Monitoring Program. | NIRB |  | N/A (NIRB)
4 | NIRB to schedule periodic site visits. | NIRB |  | N/A (NIRB)
5 | Obtain all required federal and territorial permits and other approvals, and comply with the requirements of such regulatory instruments | Agnico Eagle CIRNAC NWB NRCan TC DFO |  | The list of permits and active authorizations is provided in Section 10.1 of the Annual Report. | 2025 Annual Report, Section 10.1 | Our review did not find any issues with respect to this commitment. | DFO specific Reporting Tracking Table is provided in Appendix 32. DFO issued two Fisheries Act Authorizations, three Letters of Advice, and one Letter of Advice Amendment, to the Proponent in 2025. |  |  | Based on the information provided by Agnico Eagle in the 2025 Annual Report, this statement is accurate with respect to project activities subject to TC's mandate. TC-03: Two NPP approvals continue: 2010-600573 (Bridge, Meliadine River) and 2019-600003 (Outfall/diffuser, Melvin Bay). In 2025 AEM provided updated alignment drawings for the outfall/diffuser; as changes were minor and did not increase interference to navigation, the existing approval was updated. NPP carried out no inspections and received no navigation complaints in 2025. The five waterways dewatered in 2025 (and others planned) were reviewed and determined non-navigable, so no approvals are required. TC-01: The oil handling facility is in compliance with regulatory requirements per Part 8 of the Canada Shipping Act, 2001; no inspection was carried out in 2025. The Meliadine Mine facility meets the Marine Transportation Security Regulations and remains in compliance; the Occasional-use Marine Facility certificate is current and valid. No enforcement activity was undertaken or required by Transport Canada in 2025.
6 | Report any non-compliance as required by law immediately and take prompt and appropriate remedial action | Agnico Eagle CIRNAC NWB NRCan TC ECCC DFO |  | Reportable environmental incidents are detailed in Section 6 of the Annual Report. A table of inspections and site visits by regulators is provided in Section 10.2 of the Annual Report. Non compliances and remedial actions are reported. | 2025 Annual Report, Sections 6 and 10.2 | Our review did not find any issues with respect to this commitment. | DFO confirms the Proponent takes prompt action to report and remedy any non-compliances. DFO confirms the Proponent is not in contravention of the Fisheries Act. | Refer to ECCC Comment #9. Conclusion : Effluent quality at MEL-14 met MDMER requirements during all discharge periods in 2025; no instances of non-compliance were identified under the Fisheries Act or CEPA; administrative non-compliance was identified for incomplete submission of Q2 and Q3 MDMER reports, but no enforcement action was necessary as the non-compliance was corrected immediately. |  | Based on the information provided by Agnico Eagle in the 2025 Annual Report, this statement is accurate with respect to project activities subject to TC's mandate.
7 | The Proponent shall meet with the relevant licensing authorities before construction begins to discuss posting adequate performance bonding. Licensing authorities should take all necessary steps to ensure sufficient security is in place prior to construction | Agnico Eagle CIRNAC NWB NRCan TC DFO |  | Tracked in NWB process under the Water Licence. |  | Our review did not find any issues with respect to this commitment. | The Proponent provided a Letter of Credit to DFO during the Fisheries Act Authorization process. |  |  | Not applicable for TC
8 | Report methods used to collect and analyze monitoring data and include metadata (e.g., date, time, location). | Agnico Eagle |  | The information is included in the Annual Report. | 2025 Annual Report
9 | Make significant monitoring results and/or summaries of significant results available in English and Inuktitut, to the extent feasible | Agnico Eagle |  | Summaries of monitoring results in Inuktitut are included in Appendix of the Annual Report. | 2025 Annual Report, Appendix 40
10 | Maintain the records, including results, of all Project-related monitoring data and analysis for the life of the Project, including closure and post-closure monitoring | Agnico Eagle |  | Records of monitoring data are maintained.
11 | Maintain an up-to-date Environmental Impact Statement and updated environmental monitoring programs developed for the Project as new information is collected | Agnico Eagle |  | Updated management plans are submitted with Annual Reports and are available on the Agnico Eagle Nunavut website (https://aemnunavut.ca/meliadine-documents/).
12 | Establish a Project-specific web portal or web page as a means of making all non-confidential monitoring and reporting information associated with the Project available to the general public | Agnico Eagle |  | Management Plans and Annual Reports are posted on the Agnico Eagle Nunavut website (https://aemnunavut.ca/meliadine-documents/).
13 | Provide ongoing opportunities for consultation and comment on any substantive revisions to the Project-specific monitoring program, modelling, studies, management plans, management measures, and reporting | Agnico Eagle |  | Agnico Eagle participates in the project-specific Inuit Environmental Advisory Committee (IEAC) and Socio-Economic Monitoring Working Group (SEMWG) to review and update environmental and socio-economic management and monitoring plans.
14 | To the extent feasible, the NIRB will provide an opportunity for comment on any substantive revisions to the Project-specific monitoring, modelling, studies, management plans, management measures, and reporting provided by the Proponent under the Project Certificate | NIRB |  | N/A (NIRB)