## Sheet1
NIRB File No: 12MN036 |  | Project name: Back River Gold Mine Project |  | Project Certificate No. 007, Amendment 01
TC No. | Term and Condition Summary | Responsible Party / Authorities | Associated Plan(s) | Proponent Submission or Summary | Reference Section (Annual Report) | Comments from Responsible Parties | Additional Comments
1 | Have an Air Quality Monitoring and Management Plan in place. | B2Gold | Air Quality Monitoring and Management Plan (March 2026) | B2Gold Nunavut’s Air Quality Monitoring and Management Plan (AQMMP) was last updated in March 2026 and is provided to the NIRB with this submission. B2Gold Nunavut has confirmed that it is available on the NIRB Public Registry and on the B2Gold Nunavut Public website. B2Gold Nunavut has reviewed this plan and confirms that it addresses all relevant PC T&C's, including T&C 1, 2, 3, 6 and 8, and provides suitable guidance for current and near future site activities. | 4.5.1 TC1
2 | Demonstrate that air quality emissions remain within predicted levels. | B2Gold | Air Quality Monitoring and Management Plan (March 2026) | Air quality monitoring was conducted and finding are summarized in the NIRB Annual Report (TC2). Notably, monthly concentrations of NO2 and fixed dustfall measured at the four passive air quality stations near the Goose Plant Site in 2025 are on average, modestly higher than measured concentrations in 2024. This increase in concentrations is expected as construction activities at the Goose Plant Site increased in 2025 and the Project went into its operation phase. | 4.5.1 TC2
3 | Have a Dust Management and Monitoring Plan in place. | B2Gold | Air Quality Monitoring and Management Plan (March 2026), Section 6.1.2 (Fugitive Dust Reduction Plan), Section 8 | The Fugitive Dust Reduction Plan (FDRP) was implemented in 2025 and dust monitoring was conducted in alignment with the FDRP. See T&C 3 for details on dust monitoring results. The FDRP and AQMMP were updated in March 2026 to align with advances to monitoring technologies and to reflect the current understanding of the Project. | 4.5.1 TC3
4 | Have an Incineration Management Plan in place. | B2Gold | Incinerator Management Plan (June 2020). | B2Gold Nunavut’s Incineration Management Plan (IMP) was last updated in June 2020. B2Gold Nunavut has confirmed that it is available on the NIRB Public Registry. The NWB approved the IMP with the issuance of the amended water licence. | 4.5.1 TC4
5 | Provide the results of stack testing conducted on incinerators. | B2Gold | Incinerator Management Plan (June 2020). | B2Gold Nunavut confirms incinerator stack testing at Goose will proceed in 2026 and results will be provided in the 2026 Annual Report. | 4.5.1 TC5
6 | Maintain a Greenhouse Gas (GHG) Reduction Plan. | B2Gold | Air Quality Monitoring and Management Plan (March 2026), Section 6.1.1 | B2Gold Nunavut completed the GHG tracking program in 2025, and results are reported in the NIRB Annual Report (TC6). Total annual GHG emissions have increased in 2025 in comparison to 2024. This increase is largely attributed to an increase in diesel consumption as the Project entered its operation phase in 2025. | 4.5.1 TC6
7 | Maintain a Mine Closure and Reclamation Plan. | B2Gold | Back River Project Interim and Closure Reclamation Plan (July 2022), Various sections | The ICRP (July 2021) which included conceptual progressive revegetation program was approved by the NWB and was provided to the NIRB on December 13, 2021 . This ICRP was updated in 2022/23 as part of the Energy Centre Project. The ICRP addresses PC T&C's 7, 15, 35, and 36. | 4.5.1 TC7
8 | Provide a summary of meteorological conditions experienced within the project. | B2Gold | Air Quality Monitoring and Management Plan (July 2019), Section 7.4 | Detailed data regarding meterological conditions can be found in the Goose Project 2025 Annual Report T&C8 | 4.5.2 TC8
9 | Demonstrate consideration for noise reduction measures when siting and constructing the project and to demonstrate that noise level remains with reasonable limits. | B2Gold | Noise Abatement Plan (March 2025) | Noise reduction strategies continue to be executed. Personal noise monitoring completed in 2025 across multiple departments and SEGs indicates that occupational noise remains a significant exposure agent on the Goose Project. Based on the available dataset, a substantial portion of SEGs is at or above the WSCC action limit (Lex ≥ 80 dBA), and several results exceed the 85 dBA Lex occupational exposure limit. Variability within some SEG exposure ranges suggests task- and equipment-driven changes in noise exposure across shifts. These results support continued implementation of the Hearing Conservation Program, ongoing personal noise monitoring to strengthen the dataset, and continued verification of the effectiveness of existing engineering, administrative, and PPE controls. Priority follow-up in the next reporting period will focus on SEGs with the highest measured exposures and/or the widest exposure variability to confirm exposure drivers and identify additional feasible noise reduction opportunities. | 4.5.2 TC9
10 | Demonstrate consideration for noise to be further mitigated during project activities. | B2Gold | Noise Abatement Plan (March 2025) | Personal noise monitoring completed in 2025 across multiple departments and SEGs indicates that occupational noise remains a significant exposure agent on the Goose Project. Based on the available dataset, a substantial portion of SEGs is at or above the WSCC action limit (Lex ≥ 80 dBA), and several results exceed the 85 dBA Lex occupational exposure limit. Variability within some SEG exposure ranges suggests task- and equipment-driven changes in noise exposure across shifts. These results support continued implementation of the Hearing Conservation Program, ongoing personal noise monitoring to strengthen the dataset, and continued verification of the effectiveness of existing engineering, administrative, and PPE controls. Priority follow-up in the next reporting period will focus on SEGs with the highest measured exposures and/or the widest exposure variability to confirm exposure drivers and identify additional feasible noise reduction opportunities. Monitoring will continue in 2026 to further strengthen dataset robustness and evaluate the effectiveness of ongoing mitigation measures. | 4.5.3 TC10
11 | Conduct permafrost mapping to inform detailed design and plan for changing permafrost conditions. | B2Gold | Site-wide Ground Thermal Monitoring Plan (March 2025) | Permafrost mapping information in fulfillment of this Term and Condition can be found in Section 4.2 of the report entitled “Back River Project: 2025 Site-wide Ground Thermal Monitoring, March 2026‘’ (Appendix F-1) | 4.5.4 TC11
12 | Monitor and mitigate effects of the project on the permafrost. | B2Gold | Site-wide Ground Thermal Monitoring Plan (March 2025) | Instrument performance and data quality results indicate that all instruments were active, except one (compromised) which will need repair. Data quality was rated good. Data analysis results of the ground temperature for the sites monitored are provided in Appendix F-1 and F-2 | 4.5.4 TC12
13 | Undertake additional geotechnical investigations as needed to identify and mitigate project impacts on sensitive landforms. | B2Gold | Not Applicable | B2Gold Nunavut undertook a detailed geotechnical investigations in 2025. Results of these investigations can be accessed in the report entitled ‘’Goose & MLA Projects –2025 Geotechnical Inspections’’ provided in Appendix G. | 4.5.4 TC13
14 | Provide a Waste Management Plan. | B2Gold | Landfill and Waste Management Plan (March 2025) | Once approved by the NWB, the updated LWMP will be submitted to the NIRB in the following year’s annual report. | 4.5.4 TC14
15 | Have a Progressive Reclamation Plan in place. | B2Gold | Back River Project Interim and Closure Reclamation Plan (July 2022), Various sections | Progressive reclamation activities began in November 2025 and continue into 2026 with a focus on capping the Umwelt Waste Rock Storage Area (WRSA) with Non-Potentially Acid Generating (NPAG) material. A total of 41, 467 m3 of NPAG material has been placed on the Umwelt WRSA in 2025. | 4.5.4 TC15
16 | Develop site-specific quarry operation and management plans. | B2Gold | Back River Project Quarry Management Plan (November 2020) | The QMP (November 2020) was approved by the NWB with the issuance of the amended Licence 2AM-BRP1831 and was provided to the NIRB on Dec 13, 2021 . | 4.5.5 TC16
17 | Conduct tests of the tailings and treatment sludges and to evaluate the potential for remobilization of arsenic. | B2Gold | Tailings Management Plan (April 2022) | B2Gold Nunavut will conduct tests of the tailings and treatment sludges as they are produced to evaluate the potential for remobilization of arsenic from these materials. An updated Back River Project Tailings Management Plan (TMP) was included with the 2020 application for amendment of Water Licence 2AM-BRP1831. This TMP addressed the commitment to evaluate the potential for remobilization of arsenic in tailings and treatment sludges and was approved by the NWB with the issuance of the amended Licence 2AM-BRP1831 and a copy was provided to the NIRB. Sabina has subsequently reviewed and updated the TMP and provided an April 2022 TMP to the NWB for review and approval. | 4.5.6 TC17
18 | Undertake an infill Geotechnical Characterization Program. | B2Gold | Not Applicable | Sabina completed an initial infill geotechnical drill program at the Goose Property in March and April of 2018. Drilling was focused on understanding proposed water management infrastructure foundations and included drill holes targeting the western ridge and the TSF Containment Dam. Field permeability (packer testing) was also completed on a subset of the drill holes. Initial results of drilling at the western ridge suggest the area does not have high permeability, with few joints and fractures present, as well as clay infilling and no visible ice within the drill hole. Further geotechnical drilling was undertaken in 2021; however, the program did not focus on the TSF Containment Dam but other key infrastructure locations. | 4.5.6 TC18
19 | Maintain a Saline Water Management Plan. | B2Gold | Water Management Plan, (Version 5, May 2024) | As a requirement of the amended water licence, the WMP (and associated Saline Water Management Plan) was further revised and an updated. An updated WMP was provided to the NWB in May 2024 and approved in August 2024. B2Gold Nunavut attached a copy of the approved updated Water Management Plan (Version 5, May 2024) in the 2024 annual report. B2Gold Nunavut highlights that no changes were made to the Saline Water Management Plan as part of this update. | 4.5.6 TC19
20 | Develop a Thermal Monitoring Plan. | B2Gold | Thermal Monitoting Plan (March 2025) | The ground thermal monitoring plan was provided in 2024. The 2025 version is provided as part of the 2025 NIRB annual report (See Appendix F-2). | 4.5.6 TC20
21 | Maintain an Aquatic Effects Monitoring Plan and submit results annually. | B2Gold | Aquatic Effects Management Plan (December 2025) | A summary of the results of the 2025 AEMP monitoring is provided in 2025 AEMP Annual Report provided (Appendix H). Comments on the updated AEMP version 2.0 (December 2024) were received from KIA, CIRNAC, and ECCC in April 2025, and responses provided by B2Gold Nunavut in May 2025. Follow-up comments were received from CIRNAC and responses provided in June 2025. The AEMP was updated based on the comments and finalized in December 2025. | 4.5.7 TC21
22 | Maintain a Site Water Monitoring and Management Plan that minimizes and appropriately manages all contact water. | B2Gold | Water Management Plan (May 2024) | B2Gold Nunavut executed the Water Management Plan throughout 2025. | 4.5.7 TC22
23 | Maintain an appropriate setback distance between quarries and fish-bearing or permanent waterbodies. | B2Gold | Borrow Pits and Quarry Management Plan (November 2020) | The QMP (November 2020) was approved by the NWB with the issuance of the amended Licence 2AM-BRP1831 and was provided to the NIRB on December 13, 2021. All quarries in use have been designed with appropriate setbacks for water and fish. All setbacks are described in the QMP and were adhered to in 2025, and no additional mitigations were required. | 4.5.8 TC23
24 | Prevent blockages or restrictions to fish passages. | B2Gold | Road Management Plan (October 2017) | Although an Arctic Grayling monitoring program was not conducted in 2025, the program was conducted in the spring and summer 2024. Results from the 2024 surveys are briefly summarized in the 2025 Annual Report. | 4.5.8 TC24
25 | Mitigate impacts of explosives use on fish habitat. | B2Gold DFO | Environmental Impact Assessment Statement Supporting Volume 10: Management Plans; 13. Explosives Management Plan (2013). Sabina Back River Blasting Plan for Plant Site and Portal Decline (April 2021) | No blasting occurred within or near required setbacks from fish bearing waters, as defined using DFO criteria. | 4.5.8 TC25
26 | Minimize impacts to the migration of Arctic Grayling. | B2Gold KIA DFO | Fish Offsetting Plan Version 2.0. April 2025 A virtual meeting with DFO on February 26, 2026, to update DFO on monitoring and mitigation commitments (e.g., fishway diversion) for the Goose Mine in 2026. | Although the construction of the airstrip extension and diversion of flows is not complete, on-going monitoring and inspection programs indicate that the Rascal Stream system continues to maintain fish passage and fish use of Rascal Stream West and Rascal Stream East for Arctic Grayling. See the response for Trends under No. 24. | 4.5.8 TC26
27 | Minimize impacts to freshwater fish habitat that may be used for water withdrawal. | B2Gold DFO | Fish Offsetting Plan Version 2.0. April 2025 | Winter Ice Road: Of the 118 waterbodies examined, 55 lakes were identified as being sufficient for under-ice withdrawal. No measurable effects are predicted for fish and fish habitat for the identified source lakes as the recommended under-ice volumes will be adhered to and have been acknowledged to be protective by DFO. Goose Lake: The downstream assessment of the Goose Lake water withdrawal increase on Arctic Grayling spawning and rearing habitat was included in the 2023 NIRB annual report (WSP 2024). In 2025 B2Gold Nunavut received an updated Fisheries Act Authorization (12-HCAA-CA7-00007) which included: updated hydrometric and fish monitoring and mitigation parameters, as well as reporting and offsetting requirements. B2Gold Nunavut updated the corresponding Offsetting plan which was accepted by DFO (See Appendix I). The 2025 monitoring program was implemented in accordance with the requirements of the amended Fisheries Act Authorization (FAA; Condition 3.2.3), which directs monitoring and reporting on water withdrawal activities from Goose Lake as described in Section 4.7 of the Back River Project Fish Offsetting Plan (B2Gold Nunavut 2025), Appendix I. | 4.5.8 TC27
28 | Minimize impacts to fish from the Winter Ice Road | B2Gold | Road Management Plan (October 2017) | B2Gold Nunavut files a technical memorandum with the NWB at least sixty (60) days prior to the initiation of annual Winter Ice Road (WIR) construction which outlines the planned WIR route and water withdrawal sites. Post WIR use, additional information is provided to the NWB on any deviations in WIR construction or routing. This information is available on the NWB public registry. B2Gold Nunavut also follows guidance provided by DFO in their Letter of Advice in the withdrawal of water from these sites and adhered to the volumes assessed and agreed to by DFO and the NWB. | 4.5.8 TC28
29 | Minimize impacts from Water Crossings. | B2Gold | Road Management Plan (October 2017) | See Condition 24. | 4.5.8 TC29
30 | Monitor culverts and to ensure no barriers to fish. | B2Gold | Not Applicable | See results summarized for Condition No. 24 and 26 | 4.5.8 TC30
31 | Provide monitoring updates on the Rascal Stream Fish Passage | B2Gold | Not Applicable | Not applicable. Construction on the Rascal Stream ‘Fishway’ (diversion channel) has not occurred to date. See the reply to Project Certificate Condition No. 26 for more information. | 4.5.9 TC31
32 | Minimize the Site Footprint. | B2Gold | Vegetation Monitoring Plan (January 2020). | The 2025 disturbance footprint at the Goose Project is a total of 416.3 ha total, consisting of 365.3 ha at the Goose Mine and 50.9 ha at the Marine Laydown Area (MLA). The total area of disturbance increased by 118.8 ha between 2024 and 2025, due to Project construction. Special landscape features account for 14.2 ha of the area lost in 2025 and 71.5 ha of the total area lost to date. The total disturbance footprint at Goose Mine increased by 119.5 ha. Special landscape features account for 50.7 ha of the total ecosystem types lost at the Goose Mine to date. Disturbance at the MLA covers 0.2 ha of non-vegetated ecosystems (decrease of 5.6 ha from 2024), 9.7 ha of sparsely vegetated ecosystems (0.8 ha increase from 2024), and 41.0 ha of vegetated ecosystems (4.1 ha increase from 2024). The MLA Ice Airstrip was not constructed in 2025 resulting in a decreased footprint of disturbance in non-vegetated ecosystems. The total disturbance footprint at the MLA decreased by 0.7 ha. Special landscape features account for 20.8 ha of the total ecosystem types lost at the MLA to date. | 4.5.8 TC32
33 | Prevent the introduction of Invasive Species. | B2Gold | Vegetation Monitoring Plan (January 2020). | B2Gold Nunavut maintains a VMR and SOP regarding the cleanliness of shipments. There were no new equipment and supplies to the site applicable to this condition, therefore no logs for the 2025 season. | 4.5.8 TC33
34 | Have a Vegetation Monitoring Plan in place. | B2Gold KIA GN | Vegetation Monitoring Plan (January 2020). | The Back River Vegetation Monitoring Plan (VMP; Back River Project. 2024) is designed to quantify impacts to vegetation from Project activities including the annual construction/operation of the winter ice road (WIR) and trails. In 2025, photographic monitoring was conducted at 19 monitoring sites along the WIR on August 2 and 3, 2025 (Appendix K). Over time, the monitoring plots had very little change in disturbance level, unless the alignment of the WIR changed year to year. | 4.5.8 TC34
35 | Develop a progressive revegetation program. | B2Gold | Back River Project Interim and Closure Reclamation Plan (July 2022), Various sections | The ICRP (July 2021) included conceptual progressive revegetation program was approved by the NWB and was provided to the NIRB on December 13, 2021 . This ICRP was further updated in 2022/23 as part of the amendment application process and provided to the NIRB. The ICRP addresses PC T&C's 7, 15, 35, and 36. | 4.5.8 TC35
36 | Include a revegetation strategy within its Mine Closure and Reclamation Plan. | B2Gold | Back River Project Interim and Closure Reclamation Plan (July 2022), Various sections | The ICRP (July 2021) included progressive revegetation program was approved by the NWB and was provided to the NIRB on December 13, 2021 . This ICRP was further updated in 2022 as part of the amendment application process and provided to the NIRB. The ICRP addresses PC T&C's 7, 15, 35, and 36. The updated literature review confirms limited benefits of active revegetation continue to be outweighed by their logistical and cost constraints and potential for environmental impacts, under most circumstances. The updated review highlights the importance of prioritizing natural revegetation (passive and facilitated) in most areas, and integrating this with active revegetation where needed. The updated literature review indicated that topsoil and organic layer salvage can be successful at some Arctic sites with suitable depths greater than 10-15 cm (Johnson 1987). During construction B2Gold attempted to salvage the topsoil/organic layer when stripping overburden from Echo and Umwelt Open Pits; however, the topsoil/organic horizons were minimal to non-existent and were not salvageable separately from the overburden. The overburden in these areas primarily consists of unconsolidated material (primarily sandy loam). Topsoil/organic layer salvage may be feasible at other areas of Goose Project, as indicated by the updated literature review and baseline conditions for organic thickness. Assessment of the feasibility of topsoil/organic material salvage will be completed on a site-specific basis at the Goose Project prior to future disturbance following best practices. | 4.5.8 TC36
37 | Have in place a Wildlife Mitigation and Monitoring Plan (WMMPP). | B2Gold | Back River Project Wildlife Mitigation and Monitoring Program Plan (October 2024) | The WMMPP (Version 9, September 2018) was used during 2020, the WMMPP (Version 10, October 2019) in 2021 and 2022, the WMMPP (Version 11, December 2022 and Version 12, April 2023) for 2023, and the WMMPP (Version 12, April 2023 and Version 13, October 2024) for 2024. In 2025, the WMMPP (Version 13, October 2024) was used to guide mitigation and monitoring. | 4.5.8 TC37
38 | Monitor wildlife with relevant parties. | B2Gold KIA GN | Back River Project Wildlife Mitigation and Monitoring Program Plan (October 2024), Section 7.3.2.7 Collaborative Herd-scale Monitoring. | In June and November 2025 CTAG meetings were held including representatives from the GN and KIA to discuss Project monitoring results from the previous year and plans for the upcoming year. Additionally, B2Gold Nunavut provided in-kind support to GNWT ECC caribou collar monitoring programs by providing staging for fueling for the GNWT helicopters at Goose and MLA. Updates to the WMMP Report for 2025 based on CTAG feedback include new approaches or additional information in Sections 2.4, 2.9, 3.4, 5.4, 9.1 and 9.2. | 4.5.9 TC38
39 | Have a staged project activity reduction plan to mitigate potential impacts to caribou. | B2Gold | Back River Project Wildlife Mitigation and Monitoring Program Plan (October 2024), Section 7.2.2.2 Levels of Management for Caribou during Normal Operations, Section 7.2.2.3 Management for Shifts in Calving Ranges | In 2025, the Mine shifted between Levels 2 to 4 seven times, with an increase in protection level occurring four times, and a decrease occurring three times. | 4.5.9 TC39
40 | Ensure the threshold distances used to trigger caribou mitigation consider an appropriate biological buffer and lag time when based on satellite collar data. | B2Gold KIA GN | Back River Project Wildlife Mitigation and Monitoring Program Plan (October 2024), Section 7.3.1.2 Near Real-time Collar Monitoring | From 2020 to 2025, the Proponent used the collar data plus the biological buffer listed in the WMMPP (Version 13, October 2024) to monitor the need for caribou mitigation. Reduction of project activities occurred three occasions in 2025 (Appendix C), as triggered by thresholds described in the WMMPP (Version 13, October 2024). Advancements in available collar data in 2024 include collaboration with the GNWT ECC to provide regular (3x weekly) project specific collar maps for the area around the Goose Mine, aligning with the GNWT Mobile Caribou Conservation Measures program. These improved maps allow further increased resolution relating to caribou approaching the Mine area. | 4.5.9 TC40
41 | Mitigate impacts on caribou during the July 26 to August 31 period when there is an increased potential of caribou presence. | B2Gold | Back River Project Wildlife Mitigation and Monitoring Program Plan (October 2024), Section 7.2.2.1 Management System to Reduce Disturbance to Caribou, Section 7.2.2.2 Levels of Management for Caribou during Normal Operations. | In 2025, B2Gold Nunavut followed the mitigation measures listed in the WMMPP (Version 12, April 2023 and Version 13, October 2024). A summary of blasts and pre-blast surveys completed in 2025 is reported in the 2025 WMMP Report | 4.5.9 TC41
42 | Ensure mitigation measures apply to all caribou. | B2Gold | Back River Project Wildlife Mitigation and Monitoring Program Plan (October 2024), Section 7.2.2.1 Management System to Reduce Disturbance to Caribou, Section 7.2.2.2 Levels of Management for Caribou during Normal Operations, Section 7.2.2.3 Management for Shifts in Calving Ranges | During 2025, B2Gold Nunavut followed the mitigation measures listed in the WMMPP (Version 12, April 2023 and Version 13, October 2024). | 4.5.9 TC42
43 | Develop procedures should wildlife be deemed project tolerant. | B2Gold GN | Back River Project Wildlife Mitigation and Monitoring Program Plan (October 2024), Section 7.2.4 Mitigation and Management for Direct Mortality and Injury of Caribou. | In 2025, caribou were deterred on seven occasions, including three occasions near the Goose airstrip (twice on July 15 and once October 21), once near the MLA airstrip (August 28), and three occasions near Umwelt Pit (May 3, 4, and 5). Gentle hazing methods (i.e., people walking and waving hands and slowly driving a vehicle in their direction from a distance) were applied due to risks to caribou and personnel safety from landing aircraft or proximity to pits. On all instances the caribou were successfully deterred from the area using gentle herding. All incidents and deterrence events are detailed in the 2025 WMMP Report | 4.5.9 TC43
44 | To develop mitigation measures for muskox. | B2Gold GN | Back River Project Wildlife Mitigation and Monitoring Program Plan (October 2024), 8.1.3 Mitigation and Management for Disturbance of Muskox | No triggers for muskox as outlined in the WMMPP were reached in 2025, and as a result additional mitigation was not required. | 4.5.9 TC44
45 | Mitigate potential disturbances to wildlife movement. | B2Gold | Back River Project Wildlife Mitigation and Monitoring Program Plan (October 2024), Section 7.2.3 Mitigation and Management for Disruption of Movement of Caribou, Section 9.3.1.5 Winter Ice Road Management | In 2025, the WIR was constructed in such a way as to allow caribou and other animals to cross the road. The WIR route was planned using information from the surveys conducted in 2019 and 2020 to reduce potential for interaction with potential denning habitat through avoidance. Where high-quality potential habitat overlapped the WIR route, a survey for potential dens was conducted. This survey resulted in no feasible denning habitat being identified. Snowbank heights on the WIR were kept below 1 metre in height and were feathered wherever possible to reduce roadside slope and encourage natural caribou movement. Dedicated WIR monitors (a wildlife biologist and Inuit land user) travelled the road daily (weather permitting) from March 29 – April 18 to record wildlife presence and ensure compliance with mitigations (including bank heights). | 4.5.9 TC45
46 | Report all direct wildlife mortalities. | B2Gold | Back River Project Wildlife Mitigation and Monitoring Program Plan (October 2024) | In 2025 there were 16 wildlife mortalities reported at the Goose Project, 10 were Arctic hare or unidentified Ptarmigan. Excluding Arctic hare and Ptarmigan, there were six mortalities recorded in 2025 at the Goose Project. This is comparable to previous years since construction started (2023 = 11; 2024 = 1). | 4.5.9 TC46
47 | Mitigate wildlife interaction with the attenuation ponds and/or tailings storage areas. | B2Gold KIA ECCC | Back River Project Wildlife Mitigation and Monitoring Program Plan (October 2024), Section 7.2.7 Mitigation and Management for Exposure to Contaminants by Caribou, Section 11.3.1.1 Waterbird Monitoring on Mine Ponds. Monitoring Wildlife Use of Site Ponds SOP | B2Gold Nunavut will increase monitoring frequency of the Primary Pond and the Echo Tailings Storage Facility in 2026 now that each facility has been fully commissioned and are in use. The monitoring will adhere to The SOP drafted in 2024, Monitoring Wildlife Use of Site Ponds SOP (ENV-SOP-1.21; Version E.1, December 2025). | 4.5.9 TC47
48 | Limit wildlife attraction to the project. | B2Gold | Back River Project Wildlife Mitigation and Monitoring Program Plan (October 2024), Section 9.2.6 Mitigation and Management for Attraction of Grizzly Bear and Wolverine | During 2025, there were 10 observations of grizzly bear and 11 observations of wolverine at Goose, MLA, or WIR forward camps (specifically MLA forward camp). None of these observations were the result of an animal repeatedly interacting with waste or attractants. Additionally, no wolverine or grizzly bear observations or signs were recorded during waste and building inspections that were completed regularly throughout 2025 at Goose, MLA, and the WIR forward camps. Where observations occurred within the camp perimeter, wolverines and grizzly bear were deterred by human presence, vehicles, aircraft, and bear bangers. Hazing was required for grizzly bear on five occasions and wolverine on four occasions, which are further described in Section 9 of the WMMP Report (Appendix C). In 2025, no wolverine were noted near the Goose Waste Management Facility (incinerator). One wolverine was observed walking around the incinerator at MLA Forward on January 25, 2025, however, no mitigation actions were required. | 4.5.9 TC48
49 | Report annually on the terrestrial wildlife monitoring to the Nunavut Impact Review Board. | B2Gold | Back River Project Wildlife Mitigation and Monitoring Program Plan (October 2024) | The Goose Project started construction in 2023 and continued through early 2025, with camps and infrastructure at both the Goose Mine and MLA. The Goose Project moved into operations during the second quarter of 2025. The results of wildlife monitoring in 2025 are provided in the 2025 WMMP Report | 4.5.9 TC49
50 | Report annually on the effectiveness of ongoing monitoring and mitigation efforts. | B2Gold | Back River Project Wildlife Mitigation and Monitoring Program Plan (October 2024) | During 2025, implementation of the Caribou Management System (i.e., an increase in the protection level) was required on four occasions at the Mine. Level 4 was implemented three times with blasting being suspended and reminder to site personnel on caribou mitigative measures being issued each time. | 4.5.9 TC50
51 | Establish a Caribou Technical Advisory Group (CTAG) to provide technical oversight on caribou mitigation and monitoring. | B2Gold KIA GN | Back River Project Wildlife Mitigation and Monitoring Program Plan (October 2024), Section 3.2 Caribou Technical Advisory Group | In June and November 2025, CTAG meetings were held including representatives from the GN and KIA to discuss Project monitoring results from 2024, WIR monitoring results from 2025, and plans for the 2026 monitoring year. | 4.5.9 TC51
52 | Ensure caribou protection from additional mineral exploration. | B2Gold KIA GN GNWT | Back River Project Wildlife Mitigation and Monitoring Program Plan (October 2024), in Section 6.2, Helicopter Management in Section 7.2.2.7, Caribou Management System in Section 7.2.2.1, and additional species-specific mitigations in Sections 8-12 | In 2025, all exploration drilling activities based out of the Goose Mine followed the guidance outlined in the WMMPP (B2Gold 2024). Applicable sections of the WMMPP to exploration drilling include General Mitigation and Management (waste, noise, spills) in Section 6.2, Helicopter Management in Section 7.2.2.7, Caribou Management System in Section 7.2.2.1, and additional species-specific mitigations in Sections 8-12. | 4.5.9 TC52
53 | Develop and implement mitigation measures and monitoring for birds and bird habitat. | B2Gold | Back River Project Wildlife Mitigation and Monitoring Program Plan (October 2024) | Three bird mortalities were recorded at the Goose Project in 2025. Two were suspected to be due to natural causes, including one ptarmigan and one Rough-legged Hawk. The GN Conservation Officer was contacted regarding the Rough-legged Hawk and informed of the situation. Additionally, one ptarmigan mortality associated with hitting a building window was recorded in 2025. In 2024 and 2025 avian mortality rates were reduced, which may be the result of effective adaptive management approaches (employee awareness training, signage, enforcement of speed limits). | 4.5.11 TC53
54 | Mitigate impacts to avian Species at Risk through avoidance. | B2Gold | Back River Project Wildlife Mitigation and Monitoring Program Plan (October 2024), Section 4.1 Species at Risk | During 2025, ground clearing was required during the bird breeding season between late May and late July; therefore, pre-clearing surveys were required. In total, 25 surveys were completed prior to ground clearing activities. Pre-clearing surveys identified 11 active nests, all of which belonged to upland bird species. Additionally, six active nests were incidentally recorded within the Mine footprint, five of which belonged to upland bird species, and one which belonged to a raptor species. Appropriate buffers were established and nest monitoring was completed. Setback buffers were applied to all active nests | 4.5.11 TC54
55 | Ensure that mitigation and monitoring strategies developed for Species are Risk are updated. | B2Gold | Back River Project Wildlife Mitigation and Monitoring Program Plan (October 2024), Section 4.1 Species at Risk | The species at risk table was included and updated in the 2025 WMMP Report, including the following risk rankings updates: Territorial Status Updates (NatureServe 2026): -Caribou (Dolphin and Union herd): Imperilled to Vulnerable; -Caribou (Peary Caribou): Imperilled to Vulnerable; -Red Knot (Calidris canutus islandica): Apparently Secure to Vulnerable; and -Fin Whale (Balaenoptera physalus): Unrankable to Unrankable / Not Listed Federal Status Updates (Government of Canada 2026): -Red Knot (Calidris canutus rufa): Endangered / Not Listed to Special Concern / Endangered / Endangered; and -Red Knot (Calidris canutus islandica): Special Concern to Not Listed. | 4.5.11 TC55
56 | Mitigate impacts to birds from construction and clearing activities. | B2Gold | Back River Project Wildlife Mitigation and Monitoring Program Plan (October 2024), Section 10.3.1.2 Pre-Clearing Surveys for Raptor Nests | During 2025, ground clearing was required during the bird breeding season between late May and late July, therefore pre-clearing surveys were required. In total, 25 surveys were completed prior to ground clearing activities. Pre-clearing surveys identified 11 active nests, all of which belonged to upland bird species. Additionally, six active nests were incidentally recorded within the Mine footprint, five of which belonged to upland bird species, and one which belonged to a raptor species. Appropriate buffers were established and nest monitoring was completed. Setback buffers were applied to all active nests | 4.5.11 TC56
57 | Mitigate impacts to raptors from project construction. | B2Gold GN-DOE | Back River Project Wildlife Mitigation and Monitoring Program Plan (October 2024), Section 10.2.2 Mitigation and Management for Disturbance of Raptors, Section 10.2.4 Mitigation and Management for Direct Mortality and Injury of Raptors | No deterrence or removal of raptor nests was required during Construction or Operations in 2025. No raptor nests were observed within the Mine site. One raptor nest (Common Raven) was incidentally observed at MLA in May 2025. A setback of 30 m was implemented around the nest and monitored until the nest was confirmed to be inactive. | 4.5.11 TC57
58 | Include mitigation measures within the Wildlife Mitigation and Monitoring Plan for seaducks and waterfowl. | B2Gold | Back River Project Wildlife Mitigation and Monitoring Program Plan (October 2024) | Prior to the 2025 shipping season, the Proponent provided the Marine Monitoring SOP (ENV-SOP-1.02, July 2024) to the shipping companies. During 2025, there were 8 vessel sailings servicing the Goose Project. There was one trip that traveled from the west (Tuktoyaktuk) to the MLA, and the remaining seven travelled from the east to the MLA. During 2025, marine mammal and seabird sightings were recorded by crew members on six of the vessels. From August to October, in addition to incidental sightings, 119 surveys (52 seabird surveys and 67 marine mammal surveys) were completed totaling approximately 34 hours of observation time. During 2025, 87 separate bird sightings of 446 individual birds across 15 identified species were recorded by crew members on six vessels. None of the sightings indicated requirements for management activity. | 4.5.11 TC58
59 | Report bird mortality. | B2Gold ECCC | Back River Project Wildlife Mitigation and Monitoring Program Plan (October 2024) | Three bird mortalities were recorded in 2025, with two being associated with natural causes (ptarmigan and Rough-legged Hawk) and one due to hitting a window (ptarmigan). The GN Conservation Officer was contacted regarding the Rough-legged Hawk and informed of the situation. Full details of bird mortalities are presented in the 2025 Annual Report | 4.5.11 TC59
60 | Ensure that project aircraft maintain sufficient cruising altitudes to wildlife. | B2Gold | Back River Project Wildlife Mitigation and Monitoring Program Plan (October 2024) Back River Project Standard Operating Procedure: Fixed Wing and Helicopter Operations (ENV-SOP-1.03, December 2025) | Mitigation and monitoring in 2025 were effective. Caribou were incidentally recorded near the Goose airstrip and the MLA airstrip in 2025, but no interactions between wildlife and fixed wing aircraft occurred. On four occasions, gentle hazing was successfully completed to move the caribou farther from the airstrip prior to the arrival of incoming aircrafts. On one occasion, a plane was reverted back to Yellowknife due to the presence of approximately 50 caribou near the airstrip in July. Gentle hazing and diversion of one flight was completed successfully, as described above in relation to Project Certificate Condition No. 43 and in the WMMP Report. During 2025, both fixed-wing and helicopter pilots followed guidelines set out in the WMMPP as reported in the 2025 WMMP Report. | 4.5.11 TC60
61 | Ensure aircraft are following minimum flying altitude and to maintain a daily flight log. | B2Gold | Back River Project Wildlife Mitigation and Monitoring Program Plan (October 2024) Back River Project Standard Operating Procedure: Fixed Wing and Helicopter Operations (ENV-SOP-1.03, December 2025) | Mitigation and monitoring were effective. No wildlife incidents with aircraft were recorded. | 4.5.11 TC61
62 | Maintain a marine monitoring program at the Marine Laydown Area. | B2Gold | Marine Monitoring Plan (March 2026) | Results of B2Gold Nunavut’s 2025 marine sampling can be found in Appendix N. In 2025 there was no strong evidence of Project-related effects on physical oceanography, water quality, and phytoplankton at MLA stations relative to the reference stations. However, there remains some uncertainty in the conclusion because detection limits for many metals were higher than the target detection limits in the MMP. | 4.5.12 TC62
63 | Undertake a survey of seals prior to the construction of the winter airstrip and Winter Ice Road (WIR). | B2Gold | Back River Project Wildlife Mitigation and Monitoring Program Plan (October 2024) Back River Project Standard Operating Procedure: Seal Lair Monitoring (ENV-SOP-1.04, December 2025). | During Construction in 2025, surveys for lairs were not required for the airstrip, as the airstrip was not constructed. As construction of the WIR between the MLA and the Western River occurred prior to February 15, 2025, no pre construction surveys were required. | 4.5.13 TC63
64 | Ensure shipping companies contracted have a ship-based marine mammal monitoring protocol. | B2Gold DFO | Back River Project Wildlife Mitigation and Monitoring Program Plan (October 2024), Section 14, Section 15 Back River Project Standard Operating Procedure: Marine Shipping Wildlife Mitigation and Monitoring. (ENV-SOP-1.02, December 2025) Marine Monitoring SOP (ENV-SOP-1.03, July 2024) | Prior to the 2025 shipping season, the Proponent provided the Marine Monitoring SOP (ENV-SOP-1.03, July 2024) to the shipping companies. This SOP was updated in December 2025. During 2025, there were eight vessel sailings servicing the Goose Project. There was one trip that traveled from the west (Tuktoyaktuk) to the MLA, and the remaining seven travelled from the east to the MLA. During 2025, marine mammal and seabird sightings were recorded by crew members on nine of the vessels. From August to October, in addition to incidental sightings, 119 surveys (52 seabird surveys and 67 marine mammal surveys) were completed totaling approximately 35 hours of observation time (Appendix C). During 2025, 8 separate marine mammal observations of 20 individual birds across 5 identified species were recorded. None of the sightings indicated requirements for management activity. | 4.5.13 TC64
65 | Ensure contracted shipping companies are aware of sensitive wildlife habitat and use appropriate protocols in case of a fuel accident. | B2Gold | Back River Project Wildlife Mitigation and Monitoring Program Plan (October 2024), Section 14, Section 15 Back River Project Standard Operating Procedure: Marine Shipping Wildlife Mitigation and Monitoring. (ENV-SOP-1.02, December 2025) | Sightings of marine mammals from the vessel were recorded during shipping in 2025. During 2025, 8 separate marine mammal sightings were recorded by crew members between August 13 and September 19. Five marine mammal species were observed over the 8 separate sightings: One sighting of a killer whale (Orcinus orca), five sightings of four seal species, and two sightings of unidentified seal species Results (sightings and the shipping route) are presented in the 2025 WMMP Report. Appropriate protocols were followed to reduce the potential for an accidental release of fuel or other deleterious substance into the marine environment, as per Section 6.2.3 of the WMMPP (Version 13, October 2024). No spills occurred during shipping in 2025. | 4.5.13 TC65
66 | Participate in the work of the Kitikmeot Socio-Economic Monitoring Committee (KSEMC). | B2Gold | Socio-Economic Monitoring Plan (NIRB PRI: 355414) | B2Gold Nunavut is actively involved in the KSEMC and regularly participates in its meetings when they are organized. Most recently, B2Gold Nunavut participated in an in-person meeting with the group in Cambridge Bay in October 2025. B2Gold Nunavut’s participation in the KSEMC is summarized in Section 1.2 (Socio-Economic Monitoring Requirements and Guidance) of the Socio-Economic Monitoring Report. B2Gold Nunavut’s use of community perspectives and IK in the monitoring program is described in Section 1.4 (Community Perspectives and Inuit Knowledge) of the report. | 4.6.1 TC66
67 | Develop Terms of Reference for the project-specific Socio-Economic Monitoring Working Group (SEMWG). | B2Gold KIA GN CIRNAC Hamlets | Socio-Economic Monitoring Plan (NIRB PRI: 355414) | B2Gold Nunavut’s participation in the SEMWG is described in Section 1.2 (Socio-Economic Monitoring Requirements and Guidance) of the Socio-Economic Monitoring Report. A Terms of Reference (TOR) for the SEMWG was revised in mid-2024 in consultation with SEMWG members and provided to NIRB (NIRB PRI: 351113). It is also included as an appendix to the Socio-Economic Monitoring Plan (NIRB PRI: 355414). | 4.6.1 TC67
68 | Develop a Project-specific Back River Socio-Economic Monitoring Program. | B2Gold KIA GN CIRNAC Hamlets | Socio-Economic Monitoring Plan (NIRB PRI: 355414) | A Mine monitoring framework is described in the Socio-Economic Monitoring Plan (NIRB PRI: 355414). Section 1 (Introduction) and Section 2 (Methods) of the Socio-Economic Monitoring Report also summarize the Mine’s monitoring framework. Section 2.5 summarizes any key updates and changes that have been made to the report and monitoring program since the previous year. B2Gold Nunavut’s process for adaptive management and mitigation is described in the Socio-Economic Monitoring Plan and in Section 11.2 (Adaptive Management) of the Socio-Economic Monitoring Report. Monitoring program results will continue to be presented in B2Gold Nunavut’s annual Socio-Economic Monitoring Report. | 4.6.1 TC68
69 | Analyze potential risks of temporary mine closure. | B2Gold | Temporary Mine Closure in the Kitikmeot Region: Risks and Potential Socio-Economic Effects (JPCSL 2018; NIRB PRI: 320331) | B2Gold Nunavut has prepared an analysis of the risk of temporary mine closure that considers how communities in the Kitikmeot Region may be affected by temporary closure of the Project, including socio-economic effects. B2Gold Nunavut anticipates updating this report in 2026 and will update its socio-economic management plans, where appropriate, to reflect any relevant changes. | 4.6.1 TC69
70 | Ensure Socio-Economic Management Plan and Socio-Economic Management Program address the risk and potential effects of temporary mine closure. | B2Gold | Temporary Mine Closure in the Kitikmeot Region: Risks and Potential Socio-Economic Effects (JPCSL 2018; NIRB PRI: 320331) Socio-Economic Monitoring Plan (NIRB PRI: 355414) Community Engagement Plan (NIRB PRI: 355411) Inuit Human Resources Plan (NIRB PRI: 355413) Inuit Business Development Plan (NIRB PRI: 355412) Stakeholder Grievance Mechanism (NIRB PRI: 349370) | B2Gold Nunavut provided the report ‘Temporary Mine Closure in the Kitikmeot Region: Risks and Potential Socio-Economic Effects’ (i.e., JPCSL 2018; NIRB PRI: 320331) to NIRB in September 2018. B2Gold Nunavut has provided updated versions of the following management plans to NIRB: *Socio-Economic Monitoring Plan *Community Engagement Plan *Inuit Human Resources Plan *Inuit Business Development Plan *Stakeholder Grievance Mechanism Mitigation and management measures applicable to temporary closure are included in these plans, including measures identified in JPCSL (2018; NIRB PRI: 320331). | 4.6.1 TC70
71 | Submit staff schedule information. | B2Gold | Socio-Economic Monitoring Plan (NIRB PRI: 355414) | B2Gold Nunavut has provided a staff schedule for the Mine’s 2026 operational period in Appendix C of the 2025 Socio Economic Monitoring Report submitted to NIRB. B2Gold Nunavut will submit additional staff schedules for the operations period at appropriate times in the future. | 4.6.2 TC71
72 | Provide the GN with register of Trades Workers | B2Gold GN | Socio-Economic Monitoring Plan (NIRB PRI: 355414) | Information on trades occupations, journeypersons, and apprentices working at the Mine has been provided to NIRB in Appendix D of the Socio-Economic Monitoring Report. This information was also provided directly to the GN via email in February 2026. Updated information will be reported on in B2Gold Nunavut’s NIRB Annual Report in the future. | 4.6.2 TC72
73 | Work with training organization to ensure training opportunities. | B2Gold GN | Socio-Economic Monitoring Plan (NIRB PRI: 355414) | Specific types of training programs offered at the Mine are discussed in Section 7.1.1 (Hours of Training Completed) and Section 7.1.2 (Inuit Apprenticeships) of the Socio-Economic Monitoring Report. B2Gold Nunavut has also participated in recent training-related discussions through various forums, which are summarized in Section 7.1.6 of the 2025 Socio-Economic Monitoring Report. Furthermore, the Company, GN, and KIA signed a tripartite MOU in February 2025, in which education and training have been identified as priority areas for cooperation. | 4.6.3 TC73
74 | Maintain a referenced listing of formal certificates and licences that may be acquired on-site. | B2Gold GN | Socio-Economic Monitoring Plan (NIRB PRI: 355414) | An updated listing of formal certificates and licences that may be acquired via on-site training or training obtained and supported by the Company during Mine employment has been provided in Appendix E of the 2025 Socio-Economic Monitoring Report. | 4.6.3 TC74
75 | Review education utilization rates for Project employees to identify whether employees are accessing opportunities available to them. | B2Gold GN | Socio-Economic Monitoring Plan (NIRB PRI: 355414) | B2Gold Nunavut conducted an Inuit Personnel Survey at the Mine (Goose Lake, Exploration and MLA) in October and November 2024. Survey results applicable to this Term & Condition reveal several insights, including low educational attainment rates by some Inuit personnel. A strong majority of respondents in 2024 completed their highest level of education in the Kitikmeot Region, while a notable number of the remaining respondents had completed their education in the Northwest Territories. | 4.6.3 TC75
76 | Provide second language training. | B2Gold | Socio-Economic Monitoring Plan (NIRB PRI: 355414) Inuit Human Resources Plan (NIRB PRI: 355413) | B2Gold Nunavut offers second language training courses based on demand/upon request. The Company has not yet seen a demand for these course offerings, and none have been requested by employees. B2Gold Nunavut has proactively taken other measures to reduce the potential for language barriers to Inuit employment on site (i.e. in accordance with the objective of Term & Condition No. 76), should they exist. | 4.6.3 TC76
77 | Monitor demographic changes affecting the Kitikmeot communities. | B2Gold | Socio-Economic Monitoring Plan (NIRB PRI: 355414) | This topic is addressed in Section 3.1.2 (Number of Mine Personnel) and Section 3.1.3 (Employee Relocations) of the 2025 Socio-Economic Monitoring Report. Notably, between 2022 and 2024, there were very few Nunavut-related employee relocations, whereas in 2025, 16 Inuit employees relocated out of Nunavut and 3 relocated into Nunavut. Non-Inuit relocations in 2025 included one employee moving into Nunavut (from Edmonton to Gjoa Haven). Given the increase in employee relocations in 2025, B2Gold Nunavut will attempt to better understand employee motivations for moving in their 2026 Inuit Personnel Survey. | 4.6.4 TC77
78 | Ensure Inuit Qaujimajatuqangit and Traditional Knowledge are incorporated into monitoring plans. | B2Gold KIA | Socio-Economic Monitoring Plan (NIRB PRI: 355414) | B2Gold Nunavut has developed the document Guidance for Incorporating Community Perspectives and Inuit Knowledge in the Goose Mine’s Monitoring Programs. Community perspectives and IK are currently incorporated into two monitoring reports: the Socio-Economic Monitoring Report and the Wildlife Mitigation and Monitoring Program Report. In its Annual Reports to NIRB, B2Gold Nunavut also includes a summary of community feedback received on the Mine from the previous year, example comments, and B2Gold Nunavut’s responses to key issues raised (see Section 2.2). | 4.6.5 TC78
79 | Establish an Inuit Environmental Advisory Committee (IEAC). | B2Gold KIA | Socio-Economic Monitoring Plan (NIRB PRI: 355414) | In accordance with the IIBA (KIA and B2Gold Nunavut 2018), Schedule 7.1 Section 2, the IIBA Implementation Committee has established an Inuit Environmental Advisory Committee (IEAC) for the Mine. Seven Kitikmeot Inuit with knowledge about wildlife, fisheries, traditional land use, archaeology, or water of the Mine area were appointed to the IEAC. The IEAC held its third annual meeting and a Mine site visit in June 2025. Appendix F of the Socio-Economic Monitoring Report contains additional details on the IEAC’s composition and activities in 2025, including the number of members and home communities, and a description and outcomes of work undertaken. | 4.6.5 TC79
80 | Assess potential impacts of winter ice road usage on caribou harvesting. | B2Gold | Socio-Economic Monitoring Plan (NIRB PRI: 355414) | Since 2023, B2Gold Nunavut has conducted monitoring of the Winter Ice Road (WIR) related to ongoing implementation of the Mine’s caribou protection measures. Teams dedicated to this purpose travelled the WIR daily and have made no reports of any public use of the WIR to-date. However, in 2023 and 2024, snowmobile tracks crossing over the WIR were observed in certain locations. B2Gold Nunavut is also in the beginning stages of conducting a five-year harvest study in the Mine area. Further details and results from this study, including any recorded public WIR use, will be presented in future annual reports. | 4.6.5 TC80
81 | Consult with outfitting and guiding businesses in the area to assess and monitor potential Project effects on non-traditional activities. | B2Gold | Socio-Economic Monitoring Plan (NIRB PRI: 355414) | B2Gold Nunavut has developed an Outfitting/Guiding Business Consultation Protocol. This document is presented in Appendix D of the Socio-Economic Monitoring Plan (NIRB PRI: 355414). The Company also maintains a Stakeholder Grievance Mechanism (NIRB PRI: 349370). B2Gold Nunavut issued a biennial informational letter in March 2024 (a previous biennial letter was issued in April 2022) to all companies in possession of a pending, current, or recent GN Outfitter Licence, whose community of operation included either Cambridge Bay or Kugluktuk. HTOs in Cambridge Bay, Kugluktuk, Bathurst Inlet, and Bay Chimo also received copies of this letter. No responses to this letter were received and thus no grievances pertaining to non-traditional land and resource use were identified through this process. | 4.6.6 TC81
82 | Assess archaeological and heritage resources. | B2Gold GN-CH | Cultural and Heritage Resources Plan | In 2025 no additions were proposed for the Goose Property Area (GPA), Marine Laydown Area (MLA) or Winter Ice Road (WIR) footprints, and construction activities continued within the Project footprint for those areas. No AIA studies were completed in 2025 and therefore no AIA report was required. | 4.6.7 TC82
83 | Assess and support employee access to housing. | B2Gold GN-NHC | Socio-Economic Monitoring Plan (NIRB PRI: 355414) Inuit Human Resources Plan (NIRB PRI: 355413) | At its Goose Mine Grand Opening in September 2025, B2Gold Nunavut announced an investment of $10 million to support the building of new public housing units across all five Kitikmeot communities. As part of this initiative, B2Gold Nunavut will also provide sealift support to deliver building materials, helping ensure these projects can move forward efficiently. The Company is now in the process of working with NHC and the GN to develop a detailed implementation plan for this initiative. Furthermore, the Company, GN, and KIA signed an MOU in February 2025 in which housing has been identified as one of seven priority areas for cooperation between the parties. | 4.6.8 TC83
84 | Assess and monitor project-induced effects on regional housing. | B2Gold GN-NHC | Socio-Economic Monitoring Plan (NIRB PRI: 355414) | A 2024 Inuit Personnel Survey (IPS) was conducted at Mine sites (Goose Lake, Exploration and MLA) in October and November 2024. Survey results reveal several insights, including a high percentage of respondents living in public housing and a much lower percentage living in privately owned residences. Since starting work at the Project, 21% of respondents said their interest in purchasing their own home had increased, and a small number of survey respondents had changed their residence in the past 24 months. B2Gold Nunavut is scheduled to conduct its next Inuit Personnel Survey in 2026. | 4.6.8 TC84
85 | Establish a cross-cultural awareness training. | B2Gold KIA | Socio-Economic Monitoring Plan (NIRB PRI: 355414) Inuit Human Resources Plan (NIRB PRI: 355413) | B2Gold Nunavut conducts mandatory cultural awareness training for all long-term employees and contractors. In 2025, cultural awareness training sessions were offered on 78 different dates and were delivered by members of the Company’s Indigenous & Northern Affairs team to Mine personnel. This training was conducted at Mine sites (Goose and MLA) in English and had 477 participants, 21 of whom were Inuit. | 4.6.8 TC85
86 | Monitor and mitigate for airborne actinolite fibers. | B2Gold | Back River Project Wildlife Mitigation and Monitoring Program Plan (October 2024) | Version 13 of the WMMPP (October 2024) includes the required mitigation and monitoring programs for avian wildlife in Sections 10.2.8, 11.2.8, 12.2.8, and Appendix A (Section 5). Mitigation and monitoring related to the Energy Centre has not been initiated, as construction has not started. | 4.6.9 TC86
87 | Have in place a site orientation plan. | B2Gold | Not applicable | All orientation, training and certification materials are regularly reviewed and updated on an as-needed basis. Records of orientation, training and certification are maintained and re-current training is conducted as needed. | 4.6.9 TC87
88 | Include consideration for worker safety in its winter ice road (WIR) operations. | B2Gold | Road Management Plan (2021). | B2Gold Nunavut includes, within its project design, relevant management plans and SOPs, consideration for worker safety during winter ice road operations, particularly during periods of adverse weather conditions. B2Gold Nunavut’s Back River Project Road Management Plan (RMP) includes consideration of safety considerations for the construction and use of the WIR during adverse weather conditions. To further improve worker safety during winter ice road operations, particularly during periods of adverse weather conditions, B2Gold Nunavut has received approval for the establishment of emergency shelters along the WIR in its modification application to the NIRB. B2Gold Nunavut is still constructing the emergency shelter camps along the WIR. B2Gold Nunavut will ensure that updates are made to its safety procedures throughout the life of the Project consistent with best management practices for similar ice road projects. | 4.6.9 TC88
89 | Include prevention measures for fuel spills into the marine environment and mitigating potential effects of an accidental spill. | B2Gold | Wildlife Mitigation and Monitoring Program Plan (Version 13) Oil Pollution Prevention Plan & Oil Pollution Emergency Plan (2024). Spill Contingency Plan (2017). | Due to the comparative rarity of bulk fuel spills in recent decades, technical expertise in the areas of wildlife rescue and rehabilitation has become concentrated in a small handful of companies in North America who specialize in wildlife spill response. These companies provide technical specialists and equipment and are prepared to mobilize to any site in North America to lead wildlife response activities. In 2022, the Proponent reached out to one of these companies to confirm their ability, availability, and willingness to lead a wildlife spill response at the Back River Project, should it ever become necessary. These capabilities have now been confirmed and background provided on logistical constraints and available equipment and facilities. Any wildlife-related spill response activities such as hazing or live animal retrieval will be undertaken under the guidance of a technical specialist from one of these companies, and/or as required by the Canadian Wildlife Service (for migratory birds) or Fisheries and Oceans Canada (for marine mammals) and the Nunavut DOE Wildlife Management Division | 4.7.1 TC89
90 | Maintain an Oil Pollution Emergency Plan (OPEP). | B2Gold TC | Oil Pollution Prevention Plan & Oil Pollution Emergency Plan (2024) | The Back River Project Oil Pollution Prevention Plan & Oil Pollution Emergency Plan (OPEP) was updated to reflect the 2022 fuel offload conditions and the planned offload procedure and potential response scenarios. A final version of the OPEP (February 2023) which included a list of training participants was provided to Transport Canada, as required by the Shipping Act. The OPEP includes a list of authorised personnel, staff training, and the required Northwest Territories-Nunavut spill report document. | 4.7.1 TC90
91 | Contract certified vessels for shipping and ensure awareness of the requirements. | B2Gold TC | Shipping Management Plan (2024) Oil Pollution Prevention Plan & Oil Pollution Emergency Plan (2024). Risk Management and Emergency Response Plan (2018) | On September 3, 2018, a Back River Project Shipping Management Plan, Risk Management and Emergency Response Plan, and the Oil Pollution Emergency Plan in fulfillment of Project Certificate T&C No.91., were provided to the NIRB. The Back River Project Oil Pollution Prevention Plan & Oil Pollution Emergency Plan (OPEP) is routinely updated in each year of bulk fuel transfer and was most recently updated to reflect 2025 fuel offload activities and planned 2025 activities. These plans are also provided to the shippers to ensure they are aware of their respective requirements. The plan was updated in 2024 to reflect the Ballast Water Regulations, SOR/2021-120, that came into force on June 3, 2021, and which implement the Ballast Water Management Convention in Canada. | 4.7.1 TC91
92 | Ensure availability of spill response equipment. | B2Gold | Oil Pollution Prevention Plan & Oil Pollution Emergency Plan (2023) | An inventory of spill equipment and listing of training undertaken and is provided in the OPEP. | 4.7.1 TC92
93 | Submit a post-construction depiction of the MLA. | B2Gold DFO | Not applicable | B2Gold Nunavut confirms no in-water construction occurred in the marine environment at the Marine Laydown Area in 2025. B2Gold Nunavut notes that DFO visited the project site in September of 2025 | 4.7.1 TC93
94 | Ensure fuel trucks meet industry design standards. | B2Gold | Not applicable | B2Gold Nunavut completed monthly maintenance and inspections of fuel trucks throughout 2025. | 4.7.1 TC94
95 | Prevent adverse impacts to birds from Project activities and infrastructure including wind turbines. | B2Gold | Back River Project Wildlife Mitigation and Monitoring Program Plan (October 2024) | Version 13 of the WMMPP (October 2024) includes the required mitigation and monitoring programs for avian wildlife in Sections 10.2.8, 11.2.8, 12.2.8, and Appendix A (Section 5). Mitigation and monitoring related to the Energy Centre has not been initiated, as construction has not started. | 4.5.11 TC95
96 | Assess the potential impacts of the Project and approved Modifications on wildlife harvesting in the area. | B2Gold | Not applicable | B2Gold Nunavut is in the beginning stages of conducting a five-year harvest study in the Mine area to address new Term and Condition No. 96. Fieldwork/data collection is anticipated to begin in 2026. As this Term & Condition was only recently issued, further details and results from this study will be presented in future annual reports. Relevant information will be provided in Section 10.1.5 (Other Information) of the Socio-Economic Monitoring Report. | 4.6.5 TC96
97 | Ensure that Inuit and local employment is not reduced when the transportation of fuel is reduced due to the transition from diesel generators to alternative energy sources | B2Gold | Not applicable | Construction of the Back River Energy Centre has not yet commenced. However, B2Gold Nunavut has proactively commenced development of a Workforce Transition Plan for Inuit WIR Drivers, which will be shared with NIRB once complete. | 4.6.2 TC97
Commitments, Project Certificate No. 007, Amendment 01
Commitment no. | Commitment Summary | Responsible Party / Authorities | Associated Plan(s) | Proponent Submission or Summary | Reference
1 | NIRB to appoint Monitoring Officer(s) | NIRB | Not applicable
2 | NIRB to report annually on the monitoring program (in English, Inuinnaqtun, and Inuktitut) | NIRB | Not applicable | B2Gold Nunavut has completed the Goose Project 2025 Annual Report, Submitted March 30
3 | NIRB to conduct periodic community meetings updates regarding its Monitoring Program | NIRB | Not applicable | Not applicable
4 | NIRB to schedule periodic site inspections. | NIRB | Not applicable | The Nunavut Impact Review Board (NIRB) inspected the Goose Lake Mine on August 11, 2025, and a Monitoring Report was provided in September 2025.
5 | Proponent must obtain all required federal and territorial permits and other approvals and shall comply with the requirements of such regulatory instruments. | B2Gold CIRNAC NWB NRCan TC DFO | Not applicable | B2Gold Nunavut has obtained all required federal and territorial permits and other approvals and complies with the requirements of such regulatory instruments.
6 | Duty to Comply with environmental laws and regulations and/or regulatory instruments, prompt action to remedy non-compliance and report any non-compliance. | B2Gold CIRNAC NWB NRCan TC ECCC DFO | Not applicable | B2Gold Nunavut complies with environmental laws and regulations and/or regulatory instruments, and takes action promptly to remedy non-compliance and reports any non-compliance.
7 | Posting of adequate performance bonding. | B2Gold CIRNAC NWB NRCan TC DFO
8 | Information requirements for monitoring reporting. | B2Gold | Not applicable | Not applicable
9 | Make significant monitoring results and/or summaries of significant results available in English, Inuinnaqtun, and Inuktitut, to the extent feasible. | B2Gold | Not applicable | B2Gold provides translated summaries of significant monitoring results in English, Inuinnaqtun, and Inuktitut, to the extent feasible
10 | Maintain the records, including results, of all Project-related monitoring data and analysis for the life of the Project, including closure and post-closure monitoring. | B2Gold | Not applicable | B2Gold maintains the records, including results, of all Project-related monitoring data and analysis for the life of the Project, including closure and post-closure monitoring.
11 | Maintenance of an up-to-date Environmental Impact Statement and the updated environmental monitoring programs developed for the Project as new information is collected. | B2Gold | Not applicable | B2 Gold maintenance of an up-to-date Environmental Impact Statement and the updated environmental monitoring programs developed for the Project as new information is collected.
12 | Publicly accessible Project-specific web portal or web page to make available in a central location all significant non-confidential monitoring and reporting information submitted to regulatory authorities. | B2Gold | Not applicable | B2Gold maintains a publicly accessible Project-specific web portal or web page to make available in a central location all significant non-confidential monitoring and reporting information submitted to regulatory authorities. This can be found here: https://www.b2gold.com/operations-projects/development/back-river-canada/
13 | Provide on-going opportunities for consultation and comment on any substantive revisions to the Project-specific monitoring program, modelling, studies, management plans, management measures, and reporting. | B2Gold | Not applicable | B2Gold Nunavut provides on-going opportunities for consultation and comment on any substantive revisions to the Project-specific monitoring program, modelling, studies, management plans, management measures, and reporting.
14 | To the extent feasible, the NIRB will provide an opportunity for comment on any substantive revisions to the Project-specific monitoring, modelling, studies, management plans, management measures, and reporting provided by the Proponent under the Project Certificate. | NIRB | Not applicable | Not applicable